## general_information
Ref | tracker Status | Trigger Date | Region | Country | ISO | Appeal Code | Appeal Name | Disaster Type | Classification | EWTS Varient | Achieved | Not Achieved | Missing | Achieved Early | Achieved Late | TBD | DNU | Data Completeness | General Performance
EAMozambiqueMDRM989 | NOT ACTIVE | 2024-06-20 | Africa | Mozambique |  | MDRM989 | Mozambique earthquake | Earthquake | Orange | Emergency Appeal | 3 | 0 | 4 | 7 | 10 | 0 | 3 | 0.83333 | 0.75
EANigeriaMDRN777 | NOT ACTIVE | 2024-07-15 | Africa | Nigeria |  | MDRN777 | Nigeria population movement | Population Movement | Red | Emergency Appeal | 0 | 0 | 6 | 3 | 15 | 0 | 3 | 0.75 | 0.58333
EAPeruMDRO999 | ACTIVE | 2024-08-11 | Americas | Peru |  | MDRO999 | Peru population movement | Population Movement | Orange | Emergency Appeal | 2 | 0 | 3 | 8 | 14 | 0 | 0 | 0.88889 | 0.70833
EAMaldivesMDRM787 | ACTIVE | 2024-08-28 | Asia | Maldives |  | MDRM787 | Maldives floods | Flood | Orange | Emergency Appeal | 5 | 0 | 1 | 6 | 15 | 0 | 0 | 0.96296 | 0.71154
EAJordanMDRJ000 | ACTIVE | 2024-09-01 | MENA | Jordan |  | MDRJ000 | Jordan earthquake | Earthquake | Red | Emergency Appeal | 0 | 0 | 7 | 6 | 11 | 0 | 3 | 0.70833 | 0.67647
DREFAfghanistanMDRA111 | active | 2024-06-05 | Asia | Afghanistan | AFG | MDRA111 | Afghanistan Civil Unrest | Civil Unrest | Red | DREF | 0 | 0 | 0 | 9 | 7 | 0 | 0 | 1 | 0.78125
DREFBangladeshMDRB567 | not active | 2024-07-01 | Asia | Bangladesh | BGD | MDRB567 | Bangladesh Cyclone | Cyclone | Orange | DREF | 0 | 0 | 0 | 9 | 7 | 0 | 0 | 1 | 0.78125
DREFGermanyMDRG909 | active | 2024-08-10 | Europe | Germany | DEU | MDRG909 | Germany Earthquake | Earthquake | Orange | DREF | 0 | 0 | 0 | 9 | 7 | 0 | 0 | 1 | 0.78125
DREFChileMDRC464 | active | 2024-08-20 | Americas | Chile | CHL | MDRC464 | Chile Fire | Fire | Red | DREF | 0 | 0 | 0 | 7 | 9 | 0 | 0 | 1 | 0.71875
DREFEgyptMDRE698 | not active | 2024-09-02 | MENA | Egypt | EGY | MDRE698 | Egypt Cyclone | Cyclone | Orange | DREF | 0 | 0 | 0 | 4 | 12 | 0 | 0 | 1 | 0.625
MCMRNepalMDRS2002 | active | 2024-06-10 | Asia | Nepal | NPL | MDRS2002 | Earthquake Minu South Asia | Earthquake | Orange | Multi Country | 1 | 0 | 0 | 9 | 5 | 0 | 0 | 1 | 0.83333
MCMRZambiaMDRS7890 | active | 2024-07-11 | Africa | Zambia | ZMB | MDRS7890 | Covid 19 Africa | Epidemic | Orange | Multi Country | 1 | 0 | 0 | 8 | 6 | 0 | 0 | 1 | 0.8
MCMRJordanMDRS1234 | not active | 2024-08-15 | MENA | Jordan | JOR | MDRS1234 | Civil wat MENA | Civil Unrest | Red | Multi Country | 1 | 0 | 0 | 9 | 5 | 0 | 0 | 1 | 0.83333
PCCEIraqMDRI1998 | active | 2024-07-06 | MENA | Iraq | IRQ | MDRI1998 | Iraq complex emergency | Complex Emergency | Red | Protracted | 0 | 0 | 7 | 17 | 1 | 0 | 0 | 0.72 | 0.97222
PCCENigeriaMDRN6879 | not active | 2024-08-10 | Africa | Nigeria | NGA | MDRN6879 | Nigeria population movement | Population Movement | Orange | Protracted | 4 | 0 | 1 | 18 | 2 | 0 | 0 | 0.96 | 0.95833

## area_info
Ref | Area | Achieved | Not Achieved | Missing | Achieved Early | Achieved Late | TBD | DNU | Data Completeness | General Performance
EAMozambiqueMDRM989 | assessment | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5
EANigeriaMDRN777 | assessment | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
EAPeruMDRO999 | assessment | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
EAMaldivesMDRM787 | assessment | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5
EAJordanMDRJ000 | assessment | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
EAMozambiqueMDRM989 | coordination | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 1 | 0.5
EANigeriaMDRN777 | coordination | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 1 | 0.5
EAPeruMDRO999 | coordination | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 1 | 0.875
EAMaldivesMDRM787 | coordination | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0.75
EAJordanMDRJ000 | coordination | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 1 | 0.5
EAMozambiqueMDRM989 | financial_management | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
EANigeriaMDRN777 | financial_management | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
EAPeruMDRO999 | financial_management | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
EAMaldivesMDRM787 | financial_management | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
EAJordanMDRJ000 | financial_management | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
EAMozambiqueMDRM989 | hr_planning_and_recruitement | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1
EANigeriaMDRN777 | hr_planning_and_recruitement | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
EAPeruMDRO999 | hr_planning_and_recruitement | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
EAMaldivesMDRM787 | hr_planning_and_recruitement | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
EAJordanMDRJ000 | hr_planning_and_recruitement | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
EAMozambiqueMDRM989 | information_management | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0.6 | 1
EANigeriaMDRN777 | information_management | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
EAPeruMDRO999 | information_management | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0.4 | 1
EAMaldivesMDRM787 | information_management | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
EAJordanMDRJ000 | information_management | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
EAMozambiqueMDRM989 | planning_and_resource_mobilization | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
EANigeriaMDRN777 | planning_and_resource_mobilization | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 0.75 | 0.5
EAPeruMDRO999 | planning_and_resource_mobilization | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
EAMaldivesMDRM787 | planning_and_resource_mobilization | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 0.75 | 0.5
EAJordanMDRJ000 | planning_and_resource_mobilization | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 1 | 0.625
EAMozambiqueMDRM989 | procurement_and_logistics | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0.33333 | 1
EANigeriaMDRN777 | procurement_and_logistics | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 0.66667
EAPeruMDRO999 | procurement_and_logistics | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 0.66667
EAMaldivesMDRM787 | procurement_and_logistics | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 0.66667
EAJordanMDRJ000 | procurement_and_logistics | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0.33333 | 1
EAMozambiqueMDRM989 | security | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
EANigeriaMDRN777 | security | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
EAPeruMDRO999 | security | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
EAMaldivesMDRM787 | security | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
EAJordanMDRJ000 | security | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
EAMozambiqueMDRM989 | surge | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 1
EANigeriaMDRN777 | surge | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0.5
EAPeruMDRO999 | surge | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0.83333
EAMaldivesMDRM787 | surge | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0.83333
EAJordanMDRJ000 | surge | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0.83333
DREFAfghanistanMDRA111 | assessment | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFBangladeshMDRB567 | assessment | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFGermanyMDRG909 | assessment | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5
DREFChileMDRC464 | assessment | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5
DREFEgyptMDRE698 | assessment | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFAfghanistanMDRA111 | financial_management | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
DREFBangladeshMDRB567 | financial_management | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
DREFGermanyMDRG909 | financial_management | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
DREFChileMDRC464 | financial_management | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
DREFEgyptMDRE698 | financial_management | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0.5
DREFAfghanistanMDRA111 | planning_and_resource_mobilization | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1
DREFBangladeshMDRB567 | planning_and_resource_mobilization | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0.75
DREFGermanyMDRG909 | planning_and_resource_mobilization | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1
DREFChileMDRC464 | planning_and_resource_mobilization | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0.75
DREFEgyptMDRE698 | planning_and_resource_mobilization | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
DREFAfghanistanMDRA111 | procurement_and_logistics | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
DREFBangladeshMDRB567 | procurement_and_logistics | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0.75
DREFGermanyMDRG909 | procurement_and_logistics | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
DREFChileMDRC464 | procurement_and_logistics | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0.75
DREFEgyptMDRE698 | procurement_and_logistics | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0.75
DREFAfghanistanMDRA111 | programme_delivery | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFBangladeshMDRB567 | programme_delivery | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFGermanyMDRG909 | programme_delivery | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFChileMDRC464 | programme_delivery | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFEgyptMDRE698 | programme_delivery | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFAfghanistanMDRA111 | risk_and_accountability | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1
DREFBangladeshMDRB567 | risk_and_accountability | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1
DREFGermanyMDRG909 | risk_and_accountability | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1
DREFChileMDRC464 | risk_and_accountability | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0.75
DREFEgyptMDRE698 | risk_and_accountability | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
DREFAfghanistanMDRA111 | security | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFBangladeshMDRB567 | security | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFGermanyMDRG909 | security | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFChileMDRC464 | security | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
DREFEgyptMDRE698 | security | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5
DREFAfghanistanMDRA111 | surge | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0.83333
DREFBangladeshMDRB567 | surge | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0.83333
DREFGermanyMDRG909 | surge | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 1
DREFChileMDRC464 | surge | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0.83333
DREFEgyptMDRE698 | surge | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 0.66667
MCMRNepalMDRS2002 | coordination | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
MCMRZambiaMDRS7890 | coordination | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
MCMRJordanMDRS1234 | coordination | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5
MCMRNepalMDRS2002 | financial_management | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1
MCMRZambiaMDRS7890 | financial_management | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0.75
MCMRJordanMDRS1234 | financial_management | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1
MCMRNepalMDRS2002 | hr_planning_and_recruitement | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0.75
MCMRZambiaMDRS7890 | hr_planning_and_recruitement | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
MCMRJordanMDRS1234 | hr_planning_and_recruitement | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0.5
MCMRNepalMDRS2002 | information_management | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
MCMRZambiaMDRS7890 | information_management | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
MCMRJordanMDRS1234 | information_management | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
MCMRNepalMDRS2002 | planning_and_resource_mobilization | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0.75
MCMRZambiaMDRS7890 | planning_and_resource_mobilization | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 1 | 0.875
MCMRJordanMDRS1234 | planning_and_resource_mobilization | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 1 | 0.875
MCMRNepalMDRS2002 | procurement_and_logistics | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0.83333
MCMRZambiaMDRS7890 | procurement_and_logistics | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0.83333
MCMRJordanMDRS1234 | procurement_and_logistics | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 1
MCMRNepalMDRS2002 | surge | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0.75
MCMRZambiaMDRS7890 | surge | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0.75
MCMRJordanMDRS1234 | surge | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0.75
PCCEIraqMDRI1998 | assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0
PCCENigeriaMDRN6879 | assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0
PCCEIraqMDRI1998 | coordination | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 1
PCCENigeriaMDRN6879 | coordination | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0.83333
PCCEIraqMDRI1998 | financial_management | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 1
PCCENigeriaMDRN6879 | financial_management | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 1
PCCEIraqMDRI1998 | hr_planning_and_recruitement | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1
PCCENigeriaMDRN6879 | hr_planning_and_recruitement | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1
PCCEIraqMDRI1998 | information_management | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
PCCENigeriaMDRN6879 | information_management | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0.8 | 1
PCCEIraqMDRI1998 | planning_and_resource_mobilization | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 1
PCCENigeriaMDRN6879 | planning_and_resource_mobilization | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 1
PCCEIraqMDRI1998 | procurement_and_logistics | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0.33333 | 1
PCCENigeriaMDRN6879 | procurement_and_logistics | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 1
PCCEIraqMDRI1998 | security | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5
PCCENigeriaMDRN6879 | security | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5
PCCEIraqMDRI1998 | surge | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 1
PCCENigeriaMDRN6879 | surge | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 1

## task_info
Ref | EWTS Varient | Area | Task | Status | Completed | Delta | Avg_col
EAMozambiqueMDRM989 | ea | assessment | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Achieved Late | 2024-06-24 | 4 | 0.8
EANigeriaMDRN777 | ea | assessment | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Achieved Early | 2024-07-17 | 2 | 0.8
EAPeruMDRO999 | ea | assessment | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Achieved Early | 2024-08-13 | 2 | 0.8
EAMaldivesMDRM787 | ea | assessment | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Achieved Late | 2024-09-01 | 4 | 0.8
EAJordanMDRJ000 | ea | assessment | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Achieved Early | 2024-09-03 | 2 | 0.8
EAMozambiqueMDRM989 | ea | coordination | Hold a mini summit within 48 h of the disaster | DNU | - | -1 | 0.3
EAMozambiqueMDRM989 | ea | coordination | The Movement Joint statement is produced 48h after the Mini Summit | DNU | - | -1 | 0.4
EAMozambiqueMDRM989 | ea | coordination | review/adapt membership coordination for the context for this specific emergency | DNU | - | -1 | 0.4
EAMozambiqueMDRM989 | ea | coordination | Appropriate membership coordination is in place after 24h of disaster | Achieved Late | 2024-07-05 | 15 | 0.5
EANigeriaMDRN777 | ea | coordination | Hold a mini summit within 48 h of the disaster | DNU | - | -1 | 0.3
EANigeriaMDRN777 | ea | coordination | The Movement Joint statement is produced 48h after the Mini Summit | DNU | - | -1 | 0.4
EANigeriaMDRN777 | ea | coordination | review/adapt membership coordination for the context for this specific emergency | DNU | - | -1 | 0.4
EANigeriaMDRN777 | ea | coordination | Appropriate membership coordination is in place after 24h of disaster | Achieved Late | 2024-07-29 | 14 | 0.5
EAPeruMDRO999 | ea | coordination | Hold a mini summit within 48 h of the disaster | Achieved Early | 2024-08-13 00:00:00 | 2 | 0.3
EAPeruMDRO999 | ea | coordination | The Movement Joint statement is produced 48h after the Mini Summit | Achieved Early | 2024-08-13 00:00:00 | 2 | 0.4
EAPeruMDRO999 | ea | coordination | review/adapt membership coordination for the context for this specific emergency | Achieved Early | 2024-08-15 00:00:00 | 4 | 0.4
EAPeruMDRO999 | ea | coordination | Appropriate membership coordination is in place after 24h of disaster | Achieved Late | 2024-08-28 | 17 | 0.5
EAMaldivesMDRM787 | ea | coordination | Hold a mini summit within 48 h of the disaster | Achieved Late | 2024-09-01 00:00:00 | 4 | 0.3
EAMaldivesMDRM787 | ea | coordination | The Movement Joint statement is produced 48h after the Mini Summit | Achieved Early | 2024-09-01 00:00:00 | 4 | 0.4
EAMaldivesMDRM787 | ea | coordination | review/adapt membership coordination for the context for this specific emergency | Achieved Early | 2024-09-02 00:00:00 | 5 | 0.4
EAMaldivesMDRM787 | ea | coordination | Appropriate membership coordination is in place after 24h of disaster | Achieved Late | 2024-09-15 | 18 | 0.5
EAJordanMDRJ000 | ea | coordination | Hold a mini summit within 48 h of the disaster | DNU | - | -1 | 0.3
EAJordanMDRJ000 | ea | coordination | The Movement Joint statement is produced 48h after the Mini Summit | DNU | - | -1 | 0.4
EAJordanMDRJ000 | ea | coordination | review/adapt membership coordination for the context for this specific emergency | DNU | - | -1 | 0.4
EAJordanMDRJ000 | ea | coordination | Appropriate membership coordination is in place after 24h of disaster | Achieved Late | 2024-09-12 | 11 | 0.5
EAMozambiqueMDRM989 | ea | financial_management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Achieved Late | 2024-07-04 | 14 | 0.5
EAMozambiqueMDRM989 | ea | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Achieved Late | 2024-07-07 | 17 | 0.5
EAMozambiqueMDRM989 | ea | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Late | 2024-07-10 | 20 | 0.5
EAMozambiqueMDRM989 | ea | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Late | 2024-07-12 | 22 | 0.5
EANigeriaMDRN777 | ea | financial_management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Achieved Late | 2024-07-30 | 15 | 0.5
EANigeriaMDRN777 | ea | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Achieved Late | 2024-08-02 | 18 | 0.5
EANigeriaMDRN777 | ea | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Late | 2024-08-03 | 19 | 0.5
EANigeriaMDRN777 | ea | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Late | 2024-08-06 | 22 | 0.5
EAPeruMDRO999 | ea | financial_management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Achieved Late | 2024-08-26 | 15 | 0.5
EAPeruMDRO999 | ea | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Achieved Late | 2024-08-27 | 16 | 0.5
EAPeruMDRO999 | ea | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Late | 2024-08-28 | 17 | 0.5
EAPeruMDRO999 | ea | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Late | 2024-09-01 | 21 | 0.5
EAMaldivesMDRM787 | ea | financial_management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Achieved Late | 2024-09-14 | 17 | 0.5
EAMaldivesMDRM787 | ea | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Achieved Late | 2024-09-20 | 23 | 0.5
EAMaldivesMDRM787 | ea | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Late | 2024-09-22 | 25 | 0.5
EAMaldivesMDRM787 | ea | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Late | 2024-09-25 | 28 | 0.5
EAJordanMDRJ000 | ea | financial_management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Achieved Late | 2024-09-15 | 14 | 0.5
EAJordanMDRJ000 | ea | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Achieved Late | 2024-09-19 | 18 | 0.5
EAJordanMDRJ000 | ea | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Late | 2024-09-23 | 22 | 0.5
EAJordanMDRJ000 | ea | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Late | 2024-09-25 | 24 | 0.5
EAMozambiqueMDRM989 | ea | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Achieved Early | 2024-07-01 | 11 | 0.6
EAMozambiqueMDRM989 | ea | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Achieved Early | 2024-07-02 | 12 | 0.6
EANigeriaMDRN777 | ea | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Achieved Late | 2024-07-29 | 14 | 0.6
EANigeriaMDRN777 | ea | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Achieved Late | 2024-07-30 | 15 | 0.6
EAPeruMDRO999 | ea | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Achieved Late | 2024-08-30 | 19 | 0.6
EAPeruMDRO999 | ea | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Achieved Late | 2024-09-01 | 21 | 0.6
EAMaldivesMDRM787 | ea | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Achieved Late | 2024-09-15 | 18 | 0.6
EAMaldivesMDRM787 | ea | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Achieved Late | 2024-09-18 | 21 | 0.6
EAJordanMDRJ000 | ea | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Achieved Late | 2024-09-15 | 14 | 0.6
EAJordanMDRJ000 | ea | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Achieved Late | 2024-09-15 | 14 | 0.6
EAMozambiqueMDRM989 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | - | 0 | 0.4
EAMozambiqueMDRM989 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) | Missing | - | 0 | 0.4
EAMozambiqueMDRM989 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 week) | Achieved | 2024-07-05 00:00:00 | 0 | 0.4
EAMozambiqueMDRM989 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Achieved | 2024-08-10 00:00:00 | 0 | 0.4
EAMozambiqueMDRM989 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 month) | Achieved | 2024-08-10 00:00:00 | 0 | 0.4
EANigeriaMDRN777 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | - | 0 | 0.4
EANigeriaMDRN777 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) | Missing | - | 0 | 0.4
EANigeriaMDRN777 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 week) | Missing | - | 0 | 0.4
EANigeriaMDRN777 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | - | 0 | 0.4
EANigeriaMDRN777 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 month) | Missing | - | 0 | 0.4
EAPeruMDRO999 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Achieved | 2024-08-25 00:00:00 | 0 | 0.4
EAPeruMDRO999 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) | Achieved | 2024-08-30 00:00:00 | 0 | 0.4
EAPeruMDRO999 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 week) | Missing | - | 0 | 0.4
EAPeruMDRO999 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | - | 0 | 0.4
EAPeruMDRO999 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 month) | Missing | - | 0 | 0.4
EAMaldivesMDRM787 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Achieved | 2024-08-29 00:00:00 | 0 | 0.4
EAMaldivesMDRM787 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) | Achieved | 2024-09-01 00:00:00 | 0 | 0.4
EAMaldivesMDRM787 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 week) | Achieved | 2024-09-09 00:00:00 | 0 | 0.4
EAMaldivesMDRM787 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Achieved | 2024-09-30 00:00:00 | 0 | 0.4
EAMaldivesMDRM787 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 month) | Achieved | 2024-09-30 00:00:00 | 0 | 0.4
EAJordanMDRJ000 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | - | 0 | 0.4
EAJordanMDRJ000 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) | Missing | - | 0 | 0.4
EAJordanMDRJ000 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 week) | Missing | - | 0 | 0.4
EAJordanMDRJ000 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | - | 0 | 0.4
EAJordanMDRJ000 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 month) | Missing | - | 0 | 0.4
EAMozambiqueMDRM989 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | Missing | - | 0.4
EAMozambiqueMDRM989 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) date | - | 2024-07-05 00:00:00 | Achieved
EAMozambiqueMDRM989 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Achieved | Achieved | 2024-08-10 00:00:00 | 0.4
EANigeriaMDRN777 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | Missing | - | 0.4
EANigeriaMDRN777 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) date | - | - | Missing
EANigeriaMDRN777 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | Missing | - | 0.4
EAPeruMDRO999 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Achieved | Achieved | 2024-08-25 00:00:00 | 0.4
EAPeruMDRO999 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) date | 2024-08-30 00:00:00 | - | Missing
EAPeruMDRO999 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | Missing | - | 0.4
EAMaldivesMDRM787 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Achieved | Achieved | 2024-08-29 00:00:00 | 0.4
EAMaldivesMDRM787 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) date | 2024-09-01 00:00:00 | 2024-09-09 00:00:00 | Achieved
EAMaldivesMDRM787 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Achieved | Achieved | 2024-09-30 00:00:00 | 0.4
EAJordanMDRJ000 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | Missing | - | 0.4
EAJordanMDRJ000 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) date | - | - | Missing
EAJordanMDRJ000 | ea | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | Missing | - | 0.4
EAMozambiqueMDRM989 | ea | planning_and_resource_mobilization | Disaster Brief done to inform the FAD between 48-72 h | Achieved Late | 2024-06-26 00:00:00 | 6 | 0.3
EAMozambiqueMDRM989 | ea | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Late | 2024-06-28 | 8 | 0.5
EAMozambiqueMDRM989 | ea | planning_and_resource_mobilization | Operational Strategy validated 7 days after the EA | Achieved Late | 2024-07-03 | 13 | 0.6
EAMozambiqueMDRM989 | ea | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 2 weeks of the EA | Achieved Late | 2024-07-10 | 20 | 0.5
EANigeriaMDRN777 | ea | planning_and_resource_mobilization | Disaster Brief done to inform the FAD between 48-72 h | Missing | - | -1 | 0.3
EANigeriaMDRN777 | ea | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Late | 2024-07-22 | 7 | 0.5
EANigeriaMDRN777 | ea | planning_and_resource_mobilization | Operational Strategy validated 7 days after the EA | Achieved Late | 2024-07-30 | 15 | 0.6
EANigeriaMDRN777 | ea | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 2 weeks of the EA | Achieved Late | 2024-08-15 | 31 | 0.5
EAPeruMDRO999 | ea | planning_and_resource_mobilization | Disaster Brief done to inform the FAD between 48-72 h | Achieved Late | 2024-08-20 00:00:00 | 9 | 0.3
EAPeruMDRO999 | ea | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Late | 2024-08-21 | 10 | 0.5
EAPeruMDRO999 | ea | planning_and_resource_mobilization | Operational Strategy validated 7 days after the EA | Achieved Late | 2024-08-29 | 18 | 0.6
EAPeruMDRO999 | ea | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 2 weeks of the EA | Achieved Late | 2024-09-20 | 40 | 0.5
EAMaldivesMDRM787 | ea | planning_and_resource_mobilization | Disaster Brief done to inform the FAD between 48-72 h | Missing | - | -1 | 0.3
EAMaldivesMDRM787 | ea | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Late | 2024-09-06 | 9 | 0.5
EAMaldivesMDRM787 | ea | planning_and_resource_mobilization | Operational Strategy validated 7 days after the EA | Achieved Late | 2024-09-12 | 15 | 0.6
EAMaldivesMDRM787 | ea | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 2 weeks of the EA | Achieved Late | 2024-09-25 | 28 | 0.5
EAJordanMDRJ000 | ea | planning_and_resource_mobilization | Disaster Brief done to inform the FAD between 48-72 h | Achieved Late | 2024-09-05 00:00:00 | 4 | 0.3
EAJordanMDRJ000 | ea | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Late | 2024-09-07 | 6 | 0.5
EAJordanMDRJ000 | ea | planning_and_resource_mobilization | Operational Strategy validated 7 days after the EA | Achieved Early | 2024-09-12 | 11 | 0.6
EAJordanMDRJ000 | ea | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 2 weeks of the EA | Achieved Late | 2024-10-05 | 34 | 0.5
EAMozambiqueMDRM989 | ea | procurement_and_logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Achieved Early | 2024-06-22 | 2 | 1
EAMozambiqueMDRM989 | ea | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Missing | - | -1 | 0.3
EAMozambiqueMDRM989 | ea | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | Missing | - | -1 | 0.3
EANigeriaMDRN777 | ea | procurement_and_logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Achieved Early | 2024-07-16 | 1 | 1
EANigeriaMDRN777 | ea | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Achieved Late | 2024-07-30 00:00:00 | 15 | 0.3
EANigeriaMDRN777 | ea | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | Achieved Late | 2024-08-02 00:00:00 | 18 | 0.3
EAPeruMDRO999 | ea | procurement_and_logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Achieved Early | 2024-08-11 | 0 | 1
EAPeruMDRO999 | ea | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Achieved Late | 2024-08-27 00:00:00 | 16 | 0.3
EAPeruMDRO999 | ea | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | Achieved Late | 2024-08-29 00:00:00 | 18 | 0.3
EAMaldivesMDRM787 | ea | procurement_and_logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Achieved Early | 2024-08-29 | 1 | 1
EAMaldivesMDRM787 | ea | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Achieved Late | 2024-09-16 00:00:00 | 19 | 0.3
EAMaldivesMDRM787 | ea | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | Achieved Late | 2024-09-20 00:00:00 | 23 | 0.3
EAJordanMDRJ000 | ea | procurement_and_logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Achieved Early | 2024-09-01 | 0 | 1
EAJordanMDRJ000 | ea | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Missing | - | -1 | 0.3
EAJordanMDRJ000 | ea | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | Missing | - | -1 | 0.3
EAMozambiqueMDRM989 | ea | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Achieved Early | 2024-06-21 | 1 | 0.6
EAMozambiqueMDRM989 | ea | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-06-21 | 1 | 0.9
EAMozambiqueMDRM989 | ea | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Early | 2024-06-22 | 2 | 0.9
EANigeriaMDRN777 | ea | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Achieved Late | 2024-07-18 | 3 | 0.6
EANigeriaMDRN777 | ea | surge | RR personnel Alert sent within 12h of the request | Achieved Late | 2024-07-18 | 3 | 0.9
EANigeriaMDRN777 | ea | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Late | 2024-07-20 | 5 | 0.9
EAPeruMDRO999 | ea | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Achieved Late | 2024-08-15 | 4 | 0.6
EAPeruMDRO999 | ea | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-08-11 | 0 | 0.9
EAPeruMDRO999 | ea | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Early | 2024-08-13 | 2 | 0.9
EAMaldivesMDRM787 | ea | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Achieved Late | 2024-09-01 | 4 | 0.6
EAMaldivesMDRM787 | ea | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-08-29 | 1 | 0.9
EAMaldivesMDRM787 | ea | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Early | 2024-08-30 | 2 | 0.9
EAJordanMDRJ000 | ea | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Achieved Late | 2024-09-03 | 2 | 0.6
EAJordanMDRJ000 | ea | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-09-02 | 1 | 0.9
EAJordanMDRJ000 | ea | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Early | 2024-09-03 | 2 | 0.9
DREFAfghanistanMDRA111 | dref | assessment | Initial needs assessments completed within 72 hours​ of the event. | Achieved Early | 2024-06-07 | 2 | 0.8
DREFBangladeshMDRB567 | dref | assessment | Initial needs assessments completed within 72 hours​ of the event. | Achieved Early | 2024-07-02 | 1 | 0.8
DREFGermanyMDRG909 | dref | assessment | Initial needs assessments completed within 72 hours​ of the event. | Achieved Late | 2024-08-14 | 4 | 0.8
DREFChileMDRC464 | dref | assessment | Initial needs assessments completed within 72 hours​ of the event. | Achieved Late | 2024-08-25 | 5 | 0.8
DREFEgyptMDRE698 | dref | assessment | Initial needs assessments completed within 72 hours​ of the event. | Achieved Early | 2024-09-03 | 1 | 0.8
DREFAfghanistanMDRA111 | dref | financial_management | Project funding agreements (PFAs) signed by the NS and the IFRC no longer than 7 days from the DREF approval | Achieved Late | 2024-06-20 | 15 | 0.5
DREFAfghanistanMDRA111 | dref | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF approval | Achieved Late | 2024-06-22 | 17 | 0.5
DREFAfghanistanMDRA111 | dref | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Late | 2024-06-23 | 18 | 0.5
DREFAfghanistanMDRA111 | dref | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Late | 2024-06-26 | 21 | 0.5
DREFBangladeshMDRB567 | dref | financial_management | Project funding agreements (PFAs) signed by the NS and the IFRC no longer than 7 days from the DREF approval | Achieved Late | 2024-07-19 | 18 | 0.5
DREFBangladeshMDRB567 | dref | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF approval | Achieved Late | 2024-07-22 | 21 | 0.5
DREFBangladeshMDRB567 | dref | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Late | 2024-07-24 | 23 | 0.5
DREFBangladeshMDRB567 | dref | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Late | 2024-07-27 | 26 | 0.5
DREFGermanyMDRG909 | dref | financial_management | Project funding agreements (PFAs) signed by the NS and the IFRC no longer than 7 days from the DREF approval | Achieved Late | 2024-08-30 | 20 | 0.5
DREFGermanyMDRG909 | dref | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF approval | Achieved Late | 2024-09-02 | 23 | 0.5
DREFGermanyMDRG909 | dref | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Late | 2024-09-03 | 24 | 0.5
DREFGermanyMDRG909 | dref | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Late | 2024-09-06 | 27 | 0.5
DREFChileMDRC464 | dref | financial_management | Project funding agreements (PFAs) signed by the NS and the IFRC no longer than 7 days from the DREF approval | Achieved Late | 2024-09-08 | 19 | 0.5
DREFChileMDRC464 | dref | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF approval | Achieved Late | 2024-09-10 | 21 | 0.5
DREFChileMDRC464 | dref | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Late | 2024-09-11 | 22 | 0.5
DREFChileMDRC464 | dref | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Late | 2024-09-15 | 26 | 0.5
DREFEgyptMDRE698 | dref | financial_management | Project funding agreements (PFAs) signed by the NS and the IFRC no longer than 7 days from the DREF approval | Achieved Late | 2024-09-22 | 20 | 0.5
DREFEgyptMDRE698 | dref | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF approval | Achieved Late | 2024-09-25 | 23 | 0.5
DREFEgyptMDRE698 | dref | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Late | 2024-09-26 | 24 | 0.5
DREFEgyptMDRE698 | dref | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Late | 2024-09-29 | 27 | 0.5
DREFAfghanistanMDRA111 | dref | planning_and_resource_mobilization | DREF approved within 10 days of the trigger. 14 if the NS has started responding. | Achieved Early | 2024-06-15 | 10 | 0.9
DREFAfghanistanMDRA111 | dref | planning_and_resource_mobilization | Approval by the DREF appeal manager within 24h of receiving the final package | Achieved Early | 2024-06-05 | 0 | 0.7
DREFBangladeshMDRB567 | dref | planning_and_resource_mobilization | DREF approved within 10 days of the trigger. 14 if the NS has started responding. | Achieved Early | 2024-07-12 | 11 | 0.9
DREFBangladeshMDRB567 | dref | planning_and_resource_mobilization | Approval by the DREF appeal manager within 24h of receiving the final package | Achieved Late | 2024-07-03 | 2 | 0.7
DREFGermanyMDRG909 | dref | planning_and_resource_mobilization | DREF approved within 10 days of the trigger. 14 if the NS has started responding. | Achieved Early | 2024-08-21 | 11 | 0.9
DREFGermanyMDRG909 | dref | planning_and_resource_mobilization | Approval by the DREF appeal manager within 24h of receiving the final package | Achieved Early | 2024-08-11 | 1 | 0.7
DREFChileMDRC464 | dref | planning_and_resource_mobilization | DREF approved within 10 days of the trigger. 14 if the NS has started responding. | Achieved Early | 2024-08-30 | 10 | 0.9
DREFChileMDRC464 | dref | planning_and_resource_mobilization | Approval by the DREF appeal manager within 24h of receiving the final package | Achieved Late | 2024-08-23 | 3 | 0.7
DREFEgyptMDRE698 | dref | planning_and_resource_mobilization | DREF approved within 10 days of the trigger. 14 if the NS has started responding. | Achieved Late | 2024-09-18 | 16 | 0.9
DREFEgyptMDRE698 | dref | planning_and_resource_mobilization | Approval by the DREF appeal manager within 24h of receiving the final package | Achieved Late | 2024-09-08 | 6 | 0.7
DREFAfghanistanMDRA111 | dref | procurement_and_logistics | Supply chain plan developed within 1 week of DREF approval | Achieved Late | 2024-06-21 | 16 | 0.5
DREFAfghanistanMDRA111 | dref | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Achieved Late | 2024-06-22 | 17 | 0.8
DREFBangladeshMDRB567 | dref | procurement_and_logistics | Supply chain plan developed within 1 week of DREF approval | Achieved Late | 2024-07-18 | 17 | 0.5
DREFBangladeshMDRB567 | dref | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Achieved Early | 2024-07-14 | 13 | 0.8
DREFGermanyMDRG909 | dref | procurement_and_logistics | Supply chain plan developed within 1 week of DREF approval | Achieved Late | 2024-08-29 | 19 | 0.5
DREFGermanyMDRG909 | dref | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Achieved Late | 2024-09-02 | 23 | 0.8
DREFChileMDRC464 | dref | procurement_and_logistics | Supply chain plan developed within 1 week of DREF approval | Achieved Late | 2024-09-07 | 18 | 0.5
DREFChileMDRC464 | dref | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Achieved Early | 2024-09-02 | 13 | 0.8
DREFEgyptMDRE698 | dref | procurement_and_logistics | Supply chain plan developed within 1 week of DREF approval | Achieved Late | 2024-09-25 | 23 | 0.5
DREFEgyptMDRE698 | dref | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Achieved Early | 2024-09-14 | 12 | 0.8
DREFAfghanistanMDRA111 | dref | programme_delivery | First round of payment received to the target beneficiaries four weeks after the DREF approval - 1 Month (Date) | Achieved Early | 2024-06-15 | 10 | 1
DREFBangladeshMDRB567 | dref | programme_delivery | First round of payment received to the target beneficiaries four weeks after the DREF approval - 1 Month (Date) | Achieved Early | 2024-07-12 | 11 | 1
DREFGermanyMDRG909 | dref | programme_delivery | First round of payment received to the target beneficiaries four weeks after the DREF approval - 1 Month (Date) | Achieved Early | 2024-08-21 | 11 | 1
DREFChileMDRC464 | dref | programme_delivery | First round of payment received to the target beneficiaries four weeks after the DREF approval - 1 Month (Date) | Achieved Early | 2024-08-30 | 10 | 1
DREFEgyptMDRE698 | dref | programme_delivery | First round of payment received to the target beneficiaries four weeks after the DREF approval - 1 Month (Date) | Achieved Early | 2024-09-18 | 16 | 1
DREFAfghanistanMDRA111 | dref | risk_and_accountability | Risk management one pager using country risk the dashboard developed within 48h after the approval | Achieved Early | 2024-06-06 | 1 | 0.8
DREFAfghanistanMDRA111 | dref | risk_and_accountability | Project manager and appeal manager responsibilities one pager is shared with approval (max 14 days after trigger) | Achieved Early | 2024-06-09 | 4 | 0.9
DREFBangladeshMDRB567 | dref | risk_and_accountability | Risk management one pager using country risk the dashboard developed within 48h after the approval | Achieved Early | 2024-07-02 | -1 | 0.8
DREFBangladeshMDRB567 | dref | risk_and_accountability | Project manager and appeal manager responsibilities one pager is shared with approval (max 14 days after trigger) | Achieved Early | 2024-07-12 | 11 | 0.9
DREFGermanyMDRG909 | dref | risk_and_accountability | Risk management one pager using country risk the dashboard developed within 48h after the approval | Achieved Early | 2024-08-12 | 1 | 0.8
DREFGermanyMDRG909 | dref | risk_and_accountability | Project manager and appeal manager responsibilities one pager is shared with approval (max 14 days after trigger) | Achieved Early | 2024-08-20 | 10 | 0.9
DREFChileMDRC464 | dref | risk_and_accountability | Risk management one pager using country risk the dashboard developed within 48h after the approval | Achieved Late | 2024-09-03 | 11 | 0.8
DREFChileMDRC464 | dref | risk_and_accountability | Project manager and appeal manager responsibilities one pager is shared with approval (max 14 days after trigger) | Achieved Early | 2024-08-25 | 5 | 0.9
DREFEgyptMDRE698 | dref | risk_and_accountability | Risk management one pager using country risk the dashboard developed within 48h after the approval | Achieved Late | 2024-09-23 | 15 | 0.8
DREFEgyptMDRE698 | dref | risk_and_accountability | Project manager and appeal manager responsibilities one pager is shared with approval (max 14 days after trigger) | Achieved Late | 2024-09-21 | 19 | 0.9
DREFAfghanistanMDRA111 | dref | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster (if relevant) | Achieved Early | 2024-06-06 | 1 | 0.8
DREFAfghanistanMDRA111 | dref | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-06-06 | 1 | 1
DREFAfghanistanMDRA111 | dref | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Late | 2024-06-09 | 4 | 0.7
DREFBangladeshMDRB567 | dref | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster (if relevant) | Achieved Early | 2024-07-02 | 1 | 0.8
DREFBangladeshMDRB567 | dref | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-07-02 | 1 | 1
DREFBangladeshMDRB567 | dref | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Late | 2024-07-05 | 4 | 0.7
DREFGermanyMDRG909 | dref | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster (if relevant) | Achieved Early | 2024-08-11 | 1 | 0.8
DREFGermanyMDRG909 | dref | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-08-11 | 1 | 1
DREFGermanyMDRG909 | dref | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Early | 2024-08-13 | 3 | 0.7
DREFChileMDRC464 | dref | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster (if relevant) | Achieved Late | 2024-08-22 | 2 | 0.8
DREFChileMDRC464 | dref | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-08-21 | 1 | 1
DREFChileMDRC464 | dref | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Early | 2024-08-23 | 3 | 0.7
DREFEgyptMDRE698 | dref | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster (if relevant) | Achieved Late | 2024-09-05 | 3 | 0.8
DREFEgyptMDRE698 | dref | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-09-03 | 1 | 1
DREFEgyptMDRE698 | dref | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Late | 2024-09-15 | 13 | 0.7
MCMRNepalMDRS2002 | mcmr | coordination | Establish a Multi country coordination mechanimsms with the membership for the crisis (24 hours since escalation date) | Achieved Early | 2024-06-11 | 1 | 0.83333
MCMRZambiaMDRS7890 | mcmr | coordination | Establish a Multi country coordination mechanimsms with the membership for the crisis (24 hours since escalation date) | Achieved Early | 2024-07-12 | 1 | 0.83333
MCMRJordanMDRS1234 | mcmr | coordination | Establish a Multi country coordination mechanimsms with the membership for the crisis (24 hours since escalation date) | Achieved Late | 2024-08-18 | 3 | 0.83333
MCMRNepalMDRS2002 | mcmr | financial_management | A breakdown of the Financial allocation per country is made within 5 days of the approval of the EA | Achieved Early | 2024-06-27 | 5 | 1
MCMRNepalMDRS2002 | mcmr | financial_management | Transferts to NS & IFRC Sec. Structure are made within 5 days of the allocation table | Achieved Early | 2024-06-30 | 3 | 0.83333
MCMRZambiaMDRS7890 | mcmr | financial_management | A breakdown of the Financial allocation per country is made within 5 days of the approval of the EA | Achieved Early | 2024-07-19 | 5 | 1
MCMRZambiaMDRS7890 | mcmr | financial_management | Transferts to NS & IFRC Sec. Structure are made within 5 days of the allocation table | Achieved Late | 2024-07-25 | 6 | 0.83333
MCMRJordanMDRS1234 | mcmr | financial_management | A breakdown of the Financial allocation per country is made within 5 days of the approval of the EA | Achieved Early | 2024-08-24 | 5 | 1
MCMRJordanMDRS1234 | mcmr | financial_management | Transferts to NS & IFRC Sec. Structure are made within 5 days of the allocation table | Achieved Early | 2024-08-29 | 5 | 0.83333
MCMRNepalMDRS2002 | mcmr | hr_planning_and_recruitement | Key initial longer-term positions (for the Regional/multi country level) identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Achieved Late | 2024-06-29 | 7 | 0.5
MCMRNepalMDRS2002 | mcmr | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Achieved Early | 2024-06-30 | 1 | 0.66667
MCMRZambiaMDRS7890 | mcmr | hr_planning_and_recruitement | Key initial longer-term positions (for the Regional/multi country level) identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Achieved Late | 2024-07-19 | 5 | 0.5
MCMRZambiaMDRS7890 | mcmr | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Achieved Late | 2024-07-22 | 3 | 0.66667
MCMRJordanMDRS1234 | mcmr | hr_planning_and_recruitement | Key initial longer-term positions (for the Regional/multi country level) identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Achieved Late | 2024-08-25 | 6 | 0.5
MCMRJordanMDRS1234 | mcmr | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Achieved Late | 2024-08-28 | 3 | 0.66667
MCMRNepalMDRS2002 | mcmr | information_management | A multi country dashboard is in place and updated timely to display the situation and the activities being implemented | Achieved | 2024-06-21 | 0 | 1
MCMRZambiaMDRS7890 | mcmr | information_management | A multi country dashboard is in place and updated timely to display the situation and the activities being implemented | Achieved | 2024-07-14 | 0 | 1
MCMRJordanMDRS1234 | mcmr | information_management | A multi country dashboard is in place and updated timely to display the situation and the activities being implemented | Achieved | 2024-08-18 | 0 | 1
MCMRNepalMDRS2002 | mcmr | planning_and_resource_mobilization | Disaster Brief done for the Management Call to inform the FAD between 48-72 h | Achieved Late | 2024-06-21 | 11 | 0.83333
MCMRNepalMDRS2002 | mcmr | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Early | 2024-06-22 | 1 | 1
MCMRNepalMDRS2002 | mcmr | planning_and_resource_mobilization | Operational Strategy validated 12 days after the EA | Achieved Late | 2024-06-29 | 7 | 0.5
MCMRNepalMDRS2002 | mcmr | planning_and_resource_mobilization | Supply chain plan developed for the regional needs between logs and ops within 1 week of the approved EA | Achieved Early | 2024-06-28 | 6 | 1
MCMRZambiaMDRS7890 | mcmr | planning_and_resource_mobilization | Disaster Brief done for the Management Call to inform the FAD between 48-72 h | Achieved Early | 2024-07-14 | 3 | 0.83333
MCMRZambiaMDRS7890 | mcmr | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Early | 2024-07-14 | 0 | 1
MCMRZambiaMDRS7890 | mcmr | planning_and_resource_mobilization | Operational Strategy validated 12 days after the EA | Achieved Late | 2024-07-30 | 16 | 0.5
MCMRZambiaMDRS7890 | mcmr | planning_and_resource_mobilization | Supply chain plan developed for the regional needs between logs and ops within 1 week of the approved EA | Achieved Early | 2024-07-17 | 3 | 1
MCMRJordanMDRS1234 | mcmr | planning_and_resource_mobilization | Disaster Brief done for the Management Call to inform the FAD between 48-72 h | Achieved Early | 2024-08-18 | 3 | 0.83333
MCMRJordanMDRS1234 | mcmr | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Early | 2024-08-19 | 1 | 1
MCMRJordanMDRS1234 | mcmr | planning_and_resource_mobilization | Operational Strategy validated 12 days after the EA | Achieved Late | 2024-09-01 | 13 | 0.5
MCMRJordanMDRS1234 | mcmr | planning_and_resource_mobilization | Supply chain plan developed for the regional needs between logs and ops within 1 week of the approved EA | Achieved Early | 2024-08-26 | 7 | 1
MCMRNepalMDRS2002 | mcmr | procurement_and_logistics | Supply chain plan developed for the regional needs between logs and ops within 1 week of the approved EA | Achieved Early | 2024-06-28 | 6 | 1
MCMRNepalMDRS2002 | mcmr | procurement_and_logistics | Fully approved and submitted multi country requisitions for NFIs within 1 week of the EA (when relevant) | Achieved Late | 2024-06-30 | 8 | 0.83333
MCMRNepalMDRS2002 | mcmr | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Achieved Early | 2024-07-03 | 3 | 0.83333
MCMRZambiaMDRS7890 | mcmr | procurement_and_logistics | Supply chain plan developed for the regional needs between logs and ops within 1 week of the approved EA | Achieved Early | 2024-07-17 | 3 | 1
MCMRZambiaMDRS7890 | mcmr | procurement_and_logistics | Fully approved and submitted multi country requisitions for NFIs within 1 week of the EA (when relevant) | Achieved Early | 2024-07-19 | 5 | 0.83333
MCMRZambiaMDRS7890 | mcmr | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Achieved Late | 2024-07-23 | 4 | 0.83333
MCMRJordanMDRS1234 | mcmr | procurement_and_logistics | Supply chain plan developed for the regional needs between logs and ops within 1 week of the approved EA | Achieved Early | 2024-08-26 | 7 | 1
MCMRJordanMDRS1234 | mcmr | procurement_and_logistics | Fully approved and submitted multi country requisitions for NFIs within 1 week of the EA (when relevant) | Achieved Early | 2024-08-25 | 6 | 0.83333
MCMRJordanMDRS1234 | mcmr | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Achieved Early | 2024-08-27 | 2 | 0.83333
MCMRNepalMDRS2002 | mcmr | surge | Regional RR personnel Alert sent within 12h of the request | Achieved Early | 2024-06-11 | 1 | 1
MCMRNepalMDRS2002 | mcmr | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Late | 2024-06-13 | 2 | 0.5
MCMRZambiaMDRS7890 | mcmr | surge | Regional RR personnel Alert sent within 12h of the request | Achieved Early | 2024-07-12 | 1 | 1
MCMRZambiaMDRS7890 | mcmr | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Late | 2024-07-15 | 3 | 0.5
MCMRJordanMDRS1234 | mcmr | surge | Regional RR personnel Alert sent within 12h of the request | Achieved Early | 2024-08-17 | 2 | 1
MCMRJordanMDRS1234 | mcmr | surge | Identification of 1st rotation RR personnel within 48h of the alert | Achieved Late | 2024-08-20 | 3 | 0.5
PCCEIraqMDRI1998 | pcce | coordination | Hold a mini summit within 48 h of the disaster | Achieved Early | 2024-07-08 | 2 | 0.75
PCCEIraqMDRI1998 | pcce | coordination | Review/adapt membership coordination framework for the context for this specific emergency | Achieved Early | 2024-07-08 | 2 | 1
PCCEIraqMDRI1998 | pcce | coordination | Ensure an appropriate membership coordination framework is in place after 24h of trigger | Achieved Early | 2024-07-07 | 1 | 1
PCCENigeriaMDRN6879 | pcce | coordination | Hold a mini summit within 48 h of the disaster | Achieved Late | 2024-08-13 | 3 | 0.75
PCCENigeriaMDRN6879 | pcce | coordination | Review/adapt membership coordination framework for the context for this specific emergency | Achieved Early | 2024-08-12 | 2 | 1
PCCENigeriaMDRN6879 | pcce | coordination | Ensure an appropriate membership coordination framework is in place after 24h of trigger | Achieved Early | 2024-08-11 | 1 | 1
PCCEIraqMDRI1998 | pcce | financial_management | Project agreements signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Achieved Early | 2024-07-14 | 8 | 1
PCCEIraqMDRI1998 | pcce | financial_management | After PA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Achieved Early | 2024-07-17 | 11 | 1
PCCEIraqMDRI1998 | pcce | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Early | 2024-07-18 | 12 | 1
PCCEIraqMDRI1998 | pcce | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Early | 2024-07-21 | 15 | 1
PCCENigeriaMDRN6879 | pcce | financial_management | Project agreements signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Achieved Early | 2024-08-20 | 10 | 1
PCCENigeriaMDRN6879 | pcce | financial_management | After PA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Achieved Early | 2024-08-23 | 13 | 1
PCCENigeriaMDRN6879 | pcce | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Early | 2024-08-25 | 15 | 1
PCCENigeriaMDRN6879 | pcce | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Early | 2024-08-29 | 19 | 1
PCCEIraqMDRI1998 | pcce | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Achieved Early | 2024-07-12 | 6 | 1
PCCEIraqMDRI1998 | pcce | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Achieved Early | 2024-07-14 | 8 | 1
PCCENigeriaMDRN6879 | pcce | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Achieved Early | 2024-08-18 | 8 | 1
PCCENigeriaMDRN6879 | pcce | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Achieved Early | 2024-08-21 | 11 | 1
PCCEIraqMDRI1998 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | - | 0 | 0.5
PCCEIraqMDRI1998 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) | Missing | - | 0 | 0.5
PCCEIraqMDRI1998 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 week) | Missing | - | 0 | 0.5
PCCEIraqMDRI1998 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | - | 0 | 0.5
PCCEIraqMDRI1998 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 m) | Missing | - | 0 | 0
PCCENigeriaMDRN6879 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Achieved | 2024-08-25 00:00:00 | 0 | 0.5
PCCENigeriaMDRN6879 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) | Achieved | 2024-08-25 00:00:00 | 0 | 0.5
PCCENigeriaMDRN6879 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 week) | Achieved | 2024-08-29 00:00:00 | 0 | 0.5
PCCENigeriaMDRN6879 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Achieved | 2024-08-04 00:00:00 | 0 | 0.5
PCCENigeriaMDRN6879 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 m) | Missing | - | 0 | 0
PCCEIraqMDRI1998 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | Missing | - | 0.5
PCCEIraqMDRI1998 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) date | - | - | Missing
PCCEIraqMDRI1998 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | Missing | - | 0.5
PCCENigeriaMDRN6879 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | Achieved | Achieved | 2024-08-25 00:00:00 | 0.5
PCCENigeriaMDRN6879 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) date | 2024-08-25 00:00:00 | 2024-08-29 00:00:00 | Achieved
PCCENigeriaMDRN6879 | pcce | information_management | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Achieved | Missing | 2024-08-04 00:00:00 | 0.5
PCCEIraqMDRI1998 | pcce | planning_and_resource_mobilization | Disaster Brief done for the Management Call to inform the FAD between 48-72 | Achieved Early | 2024-07-09 | 3 | 1
PCCEIraqMDRI1998 | pcce | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Early | 2024-07-06 | 0 | 1
PCCEIraqMDRI1998 | pcce | planning_and_resource_mobilization | Operational Strategy validated 10 to 14 days after the EA | Achieved Early | 2024-07-16 | 10 | 1
PCCEIraqMDRI1998 | pcce | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 3 to 4 weeks of the EA that looks at long term funding and sustianability. | Achieved Early | 2024-08-02 | 27 | 1
PCCENigeriaMDRN6879 | pcce | planning_and_resource_mobilization | Disaster Brief done for the Management Call to inform the FAD between 48-72 | Achieved Early | 2024-08-13 | 3 | 1
PCCENigeriaMDRN6879 | pcce | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Early | 2024-08-10 | 0 | 1
PCCENigeriaMDRN6879 | pcce | planning_and_resource_mobilization | Operational Strategy validated 10 to 14 days after the EA | Achieved Early | 2024-08-19 | 9 | 1
PCCENigeriaMDRN6879 | pcce | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 3 to 4 weeks of the EA that looks at long term funding and sustianability. | Achieved Early | 2024-09-01 | 22 | 1
PCCEIraqMDRI1998 | pcce | procurement_and_logistics | Initial supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Achieved Early | 2024-07-13 | 7 | 1
PCCEIraqMDRI1998 | pcce | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Missing | - | -1 | 0.5
PCCEIraqMDRI1998 | pcce | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Missing | - | -1 | 0.5
PCCENigeriaMDRN6879 | pcce | procurement_and_logistics | Initial supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Achieved Early | 2024-08-19 | 9 | 1
PCCENigeriaMDRN6879 | pcce | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Achieved Early | 2024-08-18 00:00:00 | 8 | 0.5
PCCENigeriaMDRN6879 | pcce | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Achieved Early | 2024-08-21 00:00:00 | 11 | 0.5
PCCEIraqMDRI1998 | pcce | surge | IFRC advocates with NS for the approval and use of Surge or in country capacity from movement partners within the first 5 days of the trigger | Achieved Early | 2024-07-10 | 4 | 1
PCCEIraqMDRI1998 | pcce | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-07-07 | 1 | 1
PCCEIraqMDRI1998 | pcce | surge | Identification of 1st rotation RR personnel within 5 days of the alert *if not aligned to readiness process could be slower | Achieved Early | 2024-07-11 | 5 | 1
PCCENigeriaMDRN6879 | pcce | surge | IFRC advocates with NS for the approval and use of Surge or in country capacity from movement partners within the first 5 days of the trigger | Achieved Early | 2024-08-14 | 4 | 1
PCCENigeriaMDRN6879 | pcce | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-08-11 | 1 | 1
PCCENigeriaMDRN6879 | pcce | surge | Identification of 1st rotation RR personnel within 5 days of the alert *if not aligned to readiness process could be slower | Achieved Early | 2024-08-16 | 6 | 1