## general_information
Ref | tracker Status | Trigger Date | Region | Country | ISO | Appeal Code | Appeal Name | Disaster Type | Classification | EWTS Varient | Achieved | NA | Missing | Achieved Early | Achieved Late | DNU | Data Completeness | General Performance
EAVanuatuMDRVU012 | NOT ACTIVE | 2024-12-17 | Asia | Vanuatu |  | MDRVU012 | Vanuatu Earthquake (MDRVU012) | Earthquake | Orange | Emergency Appeal | 0 | 6 | 5 | 10 | 5 | 2 | 0.75 | 0.59524
EAUgandaMDRUG055 | ACTIVE | 2025-02-17 | Africa | Uganda |  | MDRUG055 | Uganda Ebola Outbreak (MDRUG055) | Epidemic | Orange | Emergency Appeal | 0 | 8 | 5 | 11 | 2 | 2 | 0.75 | 0.57143
EAMalawiMDRMW021 | NOT ACTIVE | 2024-12-15 | Africa | Malawi |  | MDRMW021 | Malawi Cyclone chido (MDRMW021) | Cyclone | Orange | Emergency Appeal | 2 | 23 | 3 | 0 | 0 | 0 | 0.89286 | 0.08
EAMozambiqueMDRMZ026 | NOT ACTIVE | 2024-12-15 | Africa | Mozambique |  | MDRMZ026 | Mozambique Cyclone Chido (MDRMZ026) | Cyclone | Orange | Emergency Appeal | 0 | 18 | 5 | 0 | 5 | 0 | 0.82143 | 0.1087
EAComorosMDRKM013 | NOT ACTIVE | 2024-12-15 | Africa | Comoros |  | MDRKM013 | Comoros Cyclone Chido (MDRKM013) | Cyclone | Orange | Emergency Appeal | 0 | 15 | 5 | 0 | 7 | 1 | 0.78571 | 0.15909
EAMadagascarMDRMG023 | NOT ACTIVE | 2024-12-15 | Africa | Madagascar |  | MDRMG023 | Madagascar Cyclone Chido (MDRMG023) | Cyclone | Orange | Emergency Appeal | 0 | 2 | 0 | 2 | 2 | 22 | 0.21429 | 0.5
DREFMozambiqueMDRMZ026 | not active | 2024-12-15 | Africa | Mozambique |  | MDRMZ026 | Cyclone Chido Mozambique (MDRMZ026) | Cyclone | Orange | DREF | 0 | 7 | 0 | 9 | 0 | 0 | 1 | 0.5625
MCMRMDRS1005 | not active | 2024-12-23 | Africa |  |  | MDRS1005 | Africa -Cyclone Chido (MDRS1005) | Cyclone | Orange | Multi Country | 0 | 14 | 1 | 0 | 0 | 0 | 0.93333 | 0

## area_info
Ref | Area | Achieved | NA | Missing | Achieved Early | Achieved Late | DNU | Data Completeness | General Performance
EAVanuatuMDRVU012 | assessment | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0.5
EAUgandaMDRUG055 | assessment | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1
EAMalawiMDRMW021 | assessment | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
EAMozambiqueMDRMZ026 | assessment | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
EAComorosMDRKM013 | assessment | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
EAMadagascarMDRMG023 | assessment | 0 | 0 | 0 | 0 | 0 | 1 | 0
EAVanuatuMDRVU012 | coordination | 0 | 0 | 0 | 3 | 0 | 1 | 0.75 | 1
EAUgandaMDRUG055 | coordination | 0 | 0 | 0 | 2 | 0 | 2 | 0.5 | 1
EAMalawiMDRMW021 | coordination | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0
EAMozambiqueMDRMZ026 | coordination | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 0.25
EAComorosMDRKM013 | coordination | 0 | 1 | 0 | 0 | 2 | 1 | 0.75 | 0.33333
EAMadagascarMDRMG023 | coordination | 0 | 0 | 0 | 1 | 0 | 3 | 0.25 | 1
EAVanuatuMDRVU012 | financial_management | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0
EAUgandaMDRUG055 | financial_management | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 1
EAMalawiMDRMW021 | financial_management | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0
EAMozambiqueMDRMZ026 | financial_management | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0
EAComorosMDRKM013 | financial_management | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 0.25
EAMadagascarMDRMG023 | financial_management | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 0.25
EAVanuatuMDRVU012 | hr_planning_and_recruitement | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0.25
EAUgandaMDRUG055 | hr_planning_and_recruitement | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0
EAMalawiMDRMW021 | hr_planning_and_recruitement | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0
EAMozambiqueMDRMZ026 | hr_planning_and_recruitement | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0
EAComorosMDRKM013 | hr_planning_and_recruitement | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0.25
EAMadagascarMDRMG023 | hr_planning_and_recruitement | 0 | 0 | 0 | 0 | 0 | 2 | 0
EAVanuatuMDRVU012 | information_management | 0 | 0 | 5 | 0 | 0 | 0 | 0
EAUgandaMDRUG055 | information_management | 0 | 0 | 5 | 0 | 0 | 0 | 0
EAMalawiMDRMW021 | information_management | 2 | 0 | 3 | 0 | 0 | 0 | 0.4 | 1
EAMozambiqueMDRMZ026 | information_management | 0 | 0 | 5 | 0 | 0 | 0 | 0
EAComorosMDRKM013 | information_management | 0 | 0 | 5 | 0 | 0 | 0 | 0
EAMadagascarMDRMG023 | information_management | 0 | 0 | 0 | 0 | 0 | 5 | 0
EAVanuatuMDRVU012 | planning_and_resource_mobilization | 0 | 0 | 0 | 1 | 3 | 1 | 0.8 | 0.625
EAUgandaMDRUG055 | planning_and_resource_mobilization | 0 | 2 | 0 | 3 | 0 | 0 | 1 | 0.6
EAMalawiMDRMW021 | planning_and_resource_mobilization | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0
EAMozambiqueMDRMZ026 | planning_and_resource_mobilization | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0
EAComorosMDRKM013 | planning_and_resource_mobilization | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0
EAMadagascarMDRMG023 | planning_and_resource_mobilization | 0 | 0 | 0 | 0 | 0 | 5 | 0
EAVanuatuMDRVU012 | procurement_and_logistics | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 1
EAUgandaMDRUG055 | procurement_and_logistics | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0
EAMalawiMDRMW021 | procurement_and_logistics | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0
EAMozambiqueMDRMZ026 | procurement_and_logistics | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0.5
EAComorosMDRKM013 | procurement_and_logistics | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0.33333
EAMadagascarMDRMG023 | procurement_and_logistics | 0 | 0 | 0 | 0 | 0 | 3 | 0
EAVanuatuMDRVU012 | security | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
EAUgandaMDRUG055 | security | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1
EAMalawiMDRMW021 | security | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
EAMozambiqueMDRMZ026 | security | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
EAComorosMDRKM013 | security | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
EAMadagascarMDRMG023 | security | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1
EAVanuatuMDRVU012 | surge | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 1
EAUgandaMDRUG055 | surge | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0.33333
EAMalawiMDRMW021 | surge | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0
EAMozambiqueMDRMZ026 | surge | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0
EAComorosMDRKM013 | surge | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0
EAMadagascarMDRMG023 | surge | 0 | 0 | 0 | 0 | 0 | 3 | 0
DREFMozambiqueMDRMZ026 | assessment | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
DREFMozambiqueMDRMZ026 | financial_management | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0
DREFMozambiqueMDRMZ026 | planning_and_resource_mobilization | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 1
DREFMozambiqueMDRMZ026 | procurement_and_logistics | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0.5
DREFMozambiqueMDRMZ026 | programme_delivery | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
DREFMozambiqueMDRMZ026 | risk_and_accountability | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 1
DREFMozambiqueMDRMZ026 | security | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1
DREFMozambiqueMDRMZ026 | surge | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 1
MCMRMDRS1005 | coordination | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
MCMRMDRS1005 | financial_management | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0
MCMRMDRS1005 | hr_planning_and_recruitement | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0
MCMRMDRS1005 | information_management | 0 | 0 | 1 | 0 | 0 | 0 | 0
MCMRMDRS1005 | planning_and_resource_mobilization | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0
MCMRMDRS1005 | procurement_and_logistics | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0
MCMRMDRS1005 | surge | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0

## task_info
Ref | EWTS Varient | Area | Task | Status | Completed | Delta | Escalated | Avg_col
EAVanuatuMDRVU012 | ea | assessment | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Achieved Late | 2025-01-17 00:00:00 | -28 | Not Escalated | 0.5
EAUgandaMDRUG055 | ea | assessment | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Achieved Early | 2025-02-07 00:00:00 | 13 | Not Escalated | 0.5
EAMalawiMDRMW021 | ea | assessment | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Not Achieved | - | -365 |  | 0.5
EAMozambiqueMDRMZ026 | ea | assessment | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Not Achieved | - | -365 |  | 0.5
EAComorosMDRKM013 | ea | assessment | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Not Achieved | - | -365 |  | 0.5
EAMadagascarMDRMG023 | ea | assessment | Initial needs assessments completed and disseminated within 72 hours​ of the event. | DNU | - |  |  | 0.5
EAVanuatuMDRVU012 | ea | coordination | Hold a Mini Summit within 48 h of the disaster | Achieved Early | 2024-12-19 00:00:00 | 0 | Not Escalated | 0.25
EAVanuatuMDRVU012 | ea | coordination | The Movement Joint statement is produced 48h after the Mini Summit | DNU | - |  | Not Escalated | 0
EAVanuatuMDRVU012 | ea | coordination | review/adapt membership coordination for the context for this specific emergency | Achieved Early | 2024-12-19 00:00:00 | 5 | Not Escalated | 0.6
EAVanuatuMDRVU012 | ea | coordination | Appropriate membership coordination is in place after 24h of disaster | Achieved Early | 2024-12-18 00:00:00 | 1 | Not Escalated | 0.8
EAUgandaMDRUG055 | ea | coordination | Hold a Mini Summit within 48 h of the disaster | DNU | - |  | Not Escalated | 0.25
EAUgandaMDRUG055 | ea | coordination | The Movement Joint statement is produced 48h after the Mini Summit | DNU | - |  | Not Escalated | 0
EAUgandaMDRUG055 | ea | coordination | review/adapt membership coordination for the context for this specific emergency | Achieved Early | 2025-02-07 00:00:00 | 17 | Not Escalated | 0.6
EAUgandaMDRUG055 | ea | coordination | Appropriate membership coordination is in place after 24h of disaster | Achieved Early | 2025-02-07 00:00:00 | 12 | Not Escalated | 0.8
EAMalawiMDRMW021 | ea | coordination | Hold a Mini Summit within 48 h of the disaster | Not Achieved | - | -365 |  | 0.25
EAMalawiMDRMW021 | ea | coordination | The Movement Joint statement is produced 48h after the Mini Summit | Not Achieved | - | -365 |  | 0
EAMalawiMDRMW021 | ea | coordination | review/adapt membership coordination for the context for this specific emergency | Not Achieved | - | -365 |  | 0.6
EAMalawiMDRMW021 | ea | coordination | Appropriate membership coordination is in place after 24h of disaster | Not Achieved | - | -365 |  | 0.8
EAMozambiqueMDRMZ026 | ea | coordination | Hold a Mini Summit within 48 h of the disaster | Not Achieved | - | -365 |  | 0.25
EAMozambiqueMDRMZ026 | ea | coordination | The Movement Joint statement is produced 48h after the Mini Summit | Not Achieved | - | -365 |  | 0
EAMozambiqueMDRMZ026 | ea | coordination | review/adapt membership coordination for the context for this specific emergency | Achieved Late | 2025-02-15 00:00:00 | -55 |  | 0.6
EAMozambiqueMDRMZ026 | ea | coordination | Appropriate membership coordination is in place after 24h of disaster | Achieved Late | 2025-02-15 00:00:00 | -60 |  | 0.8
EAComorosMDRKM013 | ea | coordination | Hold a Mini Summit within 48 h of the disaster | DNU | - |  |  | 0.25
EAComorosMDRKM013 | ea | coordination | The Movement Joint statement is produced 48h after the Mini Summit | Not Achieved | - | -365 |  | 0
EAComorosMDRKM013 | ea | coordination | review/adapt membership coordination for the context for this specific emergency | Achieved Late | 2025-03-15 00:00:00 | -83 |  | 0.6
EAComorosMDRKM013 | ea | coordination | Appropriate membership coordination is in place after 24h of disaster | Achieved Late | 2025-03-15 00:00:00 | -88 |  | 0.8
EAMadagascarMDRMG023 | ea | coordination | Hold a Mini Summit within 48 h of the disaster | DNU | - |  |  | 0.25
EAMadagascarMDRMG023 | ea | coordination | The Movement Joint statement is produced 48h after the Mini Summit | DNU | - |  |  | 0
EAMadagascarMDRMG023 | ea | coordination | review/adapt membership coordination for the context for this specific emergency | DNU | - |  |  | 0.6
EAMadagascarMDRMG023 | ea | coordination | Appropriate membership coordination is in place after 24h of disaster | Achieved Early | 2024-12-16 00:00:00 | 1 |  | 0.8
EAVanuatuMDRVU012 | ea | financial_management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Not Achieved | - | -365 | Not Escalated | 0.66667
EAVanuatuMDRVU012 | ea | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Not Achieved | - | -365 | Not Escalated | 0.66667
EAVanuatuMDRVU012 | ea | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Not Achieved | - | -365 | Not Escalated | 1
EAVanuatuMDRVU012 | ea | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Not Achieved | - | -365 | Not Escalated | 1
EAUgandaMDRUG055 | ea | financial_management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Achieved Early | 2025-02-11 00:00:00 | 17 | Not Escalated | 0.66667
EAUgandaMDRUG055 | ea | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Achieved Early | 2025-02-17 00:00:00 | 14 | Not Escalated | 0.66667
EAUgandaMDRUG055 | ea | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Achieved Early | 2025-02-17 00:00:00 | 16 | Not Escalated | 1
EAUgandaMDRUG055 | ea | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Achieved Early | 2025-02-28 00:00:00 | 9 | Not Escalated | 1
EAMalawiMDRMW021 | ea | financial_management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Not Achieved | - | -365 |  | 0.66667
EAMalawiMDRMW021 | ea | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Not Achieved | - | -365 |  | 0.66667
EAMalawiMDRMW021 | ea | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Not Achieved | - | -365 |  | 1
EAMalawiMDRMW021 | ea | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Not Achieved | - | -365 |  | 1
EAMozambiqueMDRMZ026 | ea | financial_management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Not Achieved | - | -365 |  | 0.66667
EAMozambiqueMDRMZ026 | ea | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Not Achieved | - | -365 |  | 0.66667
EAMozambiqueMDRMZ026 | ea | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Not Achieved | - | -365 |  | 1
EAMozambiqueMDRMZ026 | ea | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Not Achieved | - | -365 |  | 1
EAComorosMDRKM013 | ea | financial_management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Achieved Late | 2025-02-15 00:00:00 | -51 |  | 0.66667
EAComorosMDRKM013 | ea | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Achieved Late | 2025-03-15 00:00:00 | -76 |  | 0.66667
EAComorosMDRKM013 | ea | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Not Achieved | - | -365 |  | 1
EAComorosMDRKM013 | ea | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Not Achieved | - | -365 |  | 1
EAMadagascarMDRMG023 | ea | financial_management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Achieved Late | 2025-02-15 00:00:00 | -51 |  | 0.66667
EAMadagascarMDRMG023 | ea | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Achieved Late | 2025-03-15 00:00:00 | -76 |  | 0.66667
EAMadagascarMDRMG023 | ea | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Not Achieved | - | -365 |  | 1
EAMadagascarMDRMG023 | ea | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Not Achieved | - | -365 |  | 1
EAVanuatuMDRVU012 | ea | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Achieved Late | 2025-01-17 00:00:00 | -20 | Not Escalated | 0.25
EAVanuatuMDRVU012 | ea | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Not Achieved | - | -365 | Not Escalated | 0.25
EAUgandaMDRUG055 | ea | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Not Achieved | - | -365 | Not Escalated | 0.25
EAUgandaMDRUG055 | ea | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Not Achieved | - | -365 | Not Escalated | 0.25
EAMalawiMDRMW021 | ea | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Not Achieved | - | -365 |  | 0.25
EAMalawiMDRMW021 | ea | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Not Achieved | - | -365 |  | 0.25
EAMozambiqueMDRMZ026 | ea | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Not Achieved | - | -365 |  | 0.25
EAMozambiqueMDRMZ026 | ea | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Not Achieved | - | -365 |  | 0.25
EAComorosMDRKM013 | ea | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Not Achieved | - | -365 |  | 0.25
EAComorosMDRKM013 | ea | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Achieved Late | 2025-02-15 00:00:00 | -49 |  | 0.25
EAMadagascarMDRMG023 | ea | hr_planning_and_recruitement | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | DNU | - |  |  | 0.25
EAMadagascarMDRMG023 | ea | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | DNU | - |  |  | 0.25
EAVanuatuMDRVU012 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | - |  | Not Escalated | 0.16667
EAVanuatuMDRVU012 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (72h) | Missing | - |  | Not Escalated | 0.16667
EAVanuatuMDRVU012 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 week) | Missing | - |  | Not Escalated | 0
EAVanuatuMDRVU012 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | - |  | Not Escalated | 0
EAVanuatuMDRVU012 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 month) | Missing | - |  | Not Escalated | 0
EAUgandaMDRUG055 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | - |  | Not Escalated | 0.16667
EAUgandaMDRUG055 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (72h) | Missing | - |  | Not Escalated | 0.16667
EAUgandaMDRUG055 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 week) | Missing | - |  | Not Escalated | 0
EAUgandaMDRUG055 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | - |  | Not Escalated | 0
EAUgandaMDRUG055 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 month) | Missing | - |  | Not Escalated | 0
EAMalawiMDRMW021 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (24h) | Achieved | 2025-01-15 00:00:00 |  |  | 0.16667
EAMalawiMDRMW021 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (72h) | Achieved | 2025-01-15 00:00:00 |  |  | 0.16667
EAMalawiMDRMW021 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 week) | Missing | - |  |  | 0
EAMalawiMDRMW021 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | - |  |  | 0
EAMalawiMDRMW021 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 month) | Missing | - |  |  | 0
EAMozambiqueMDRMZ026 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | - |  |  | 0.16667
EAMozambiqueMDRMZ026 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (72h) | Missing | - |  |  | 0.16667
EAMozambiqueMDRMZ026 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 week) | Missing | - |  |  | 0
EAMozambiqueMDRMZ026 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | - |  |  | 0
EAMozambiqueMDRMZ026 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 month) | Missing | - |  |  | 0
EAComorosMDRKM013 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (24h) | Missing | - |  |  | 0.16667
EAComorosMDRKM013 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (72h) | Missing | - |  |  | 0.16667
EAComorosMDRKM013 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 week) | Missing | - |  |  | 0
EAComorosMDRKM013 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (2 weeks) | Missing | - |  |  | 0
EAComorosMDRKM013 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 month) | Missing | - |  |  | 0
EAMadagascarMDRMG023 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (24h) | DNU | - |  |  | 0.16667
EAMadagascarMDRMG023 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (72h) | DNU | - |  |  | 0.16667
EAMadagascarMDRMG023 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 week) | DNU | - |  |  | 0
EAMadagascarMDRMG023 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (2 weeks) | DNU | - |  |  | 0
EAMadagascarMDRMG023 | ea | information_management | IM Snapshot is in place and updated timely to display the situation and the activities being implemented (1 month) | DNU | - |  |  | 0
EAVanuatuMDRVU012 | ea | planning_and_resource_mobilization | Disaster Brief done to inform the FAD between 48-72 h | Achieved Late | 2024-12-18 00:00:00 | -1 | Not Escalated | 0.5
EAVanuatuMDRVU012 | ea | planning_and_resource_mobilization | Approval of decision for DREF operation escalation to EA (disaster trigger date) | DNU | - |  |  | 0.33333
EAVanuatuMDRVU012 | ea | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Early | 2024-12-20 00:00:00 | 1 | Not Escalated | 0.66667
EAVanuatuMDRVU012 | ea | planning_and_resource_mobilization | Operational Strategy validated 7 days after the EA | Achieved Late | 2025-01-12 00:00:00 | -15 | Not Escalated | 0.25
EAVanuatuMDRVU012 | ea | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 2 weeks of the EA | Achieved Late | 2025-01-17 00:00:00 | -13 | Not Escalated | 0.25
EAUgandaMDRUG055 | ea | planning_and_resource_mobilization | Disaster Brief done to inform the FAD between 48-72 h | Achieved Early | 2025-02-12 00:00:00 | 5 | Not Escalated | 0.5
EAUgandaMDRUG055 | ea | planning_and_resource_mobilization | Approval of decision for DREF operation escalation to EA (disaster trigger date) | Achieved Early | 2025-02-17 00:00:00 | 3 |  | 0.33333
EAUgandaMDRUG055 | ea | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Achieved Early | 2025-02-17 00:00:00 | 4 | Not Escalated | 0.66667
EAUgandaMDRUG055 | ea | planning_and_resource_mobilization | Operational Strategy validated 7 days after the EA | Not Achieved | - | -365 | Not Escalated | 0.25
EAUgandaMDRUG055 | ea | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 2 weeks of the EA | Not Achieved | - | -365 | Not Escalated | 0.25
EAMalawiMDRMW021 | ea | planning_and_resource_mobilization | Disaster Brief done to inform the FAD between 48-72 h | Not Achieved | - | -365 |  | 0.5
EAMalawiMDRMW021 | ea | planning_and_resource_mobilization | Approval of decision for DREF operation escalation to EA (disaster trigger date) | Not Achieved | - | -365 |  | 0.33333
EAMalawiMDRMW021 | ea | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Not Achieved | - | -365 |  | 0.66667
EAMalawiMDRMW021 | ea | planning_and_resource_mobilization | Operational Strategy validated 7 days after the EA | Not Achieved | - | -365 |  | 0.25
EAMalawiMDRMW021 | ea | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 2 weeks of the EA | Not Achieved | - | -365 |  | 0.25
EAMozambiqueMDRMZ026 | ea | planning_and_resource_mobilization | Disaster Brief done to inform the FAD between 48-72 h | Not Achieved | - | -365 |  | 0.5
EAMozambiqueMDRMZ026 | ea | planning_and_resource_mobilization | Approval of decision for DREF operation escalation to EA (disaster trigger date) | Not Achieved | - | -365 |  | 0.33333
EAMozambiqueMDRMZ026 | ea | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Not Achieved | - | -365 |  | 0.66667
EAMozambiqueMDRMZ026 | ea | planning_and_resource_mobilization | Operational Strategy validated 7 days after the EA | Not Achieved | - | -365 |  | 0.25
EAMozambiqueMDRMZ026 | ea | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 2 weeks of the EA | Not Achieved | - | -365 |  | 0.25
EAComorosMDRKM013 | ea | planning_and_resource_mobilization | Disaster Brief done to inform the FAD between 48-72 h | Not Achieved | - | -365 |  | 0.5
EAComorosMDRKM013 | ea | planning_and_resource_mobilization | Approval of decision for DREF operation escalation to EA (disaster trigger date) | Not Achieved | - | -365 |  | 0.33333
EAComorosMDRKM013 | ea | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Not Achieved | - | -365 |  | 0.66667
EAComorosMDRKM013 | ea | planning_and_resource_mobilization | Operational Strategy validated 7 days after the EA | Not Achieved | - | -365 |  | 0.25
EAComorosMDRKM013 | ea | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 2 weeks of the EA | Not Achieved | - | -365 |  | 0.25
EAMadagascarMDRMG023 | ea | planning_and_resource_mobilization | Disaster Brief done to inform the FAD between 48-72 h | DNU | - |  |  | 0.5
EAMadagascarMDRMG023 | ea | planning_and_resource_mobilization | Approval of decision for DREF operation escalation to EA (disaster trigger date) | DNU | - |  |  | 0.33333
EAMadagascarMDRMG023 | ea | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | DNU | - |  |  | 0.66667
EAMadagascarMDRMG023 | ea | planning_and_resource_mobilization | Operational Strategy validated 7 days after the EA | DNU | - |  |  | 0.25
EAMadagascarMDRMG023 | ea | planning_and_resource_mobilization | A resource mobilization plan is developed and approved within 2 weeks of the EA | DNU | - |  |  | 0.25
EAVanuatuMDRVU012 | ea | procurement_and_logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Achieved Early | 2024-12-18 00:00:00 | 6 | Not Escalated | 0.5
EAVanuatuMDRVU012 | ea | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Achieved Early | 2024-12-18 00:00:00 | 10 | Not Escalated | 0.5
EAVanuatuMDRVU012 | ea | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | Achieved Early | 2024-12-20 00:00:00 | 11 | Not Escalated | 0.5
EAUgandaMDRUG055 | ea | procurement_and_logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Not Achieved | - | -365 | Not Escalated | 0.5
EAUgandaMDRUG055 | ea | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Not Achieved | - | -365 | Not Escalated | 0.5
EAUgandaMDRUG055 | ea | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | Not Achieved | - | -365 | Not Escalated | 0.5
EAMalawiMDRMW021 | ea | procurement_and_logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Not Achieved | - | -365 |  | 0.5
EAMalawiMDRMW021 | ea | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Not Achieved | - | -365 |  | 0.5
EAMalawiMDRMW021 | ea | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | Not Achieved | - | -365 |  | 0.5
EAMozambiqueMDRMZ026 | ea | procurement_and_logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Achieved Late | 2025-02-15 00:00:00 | -55 |  | 0.5
EAMozambiqueMDRMZ026 | ea | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Achieved Late | 2025-03-15 00:00:00 | -79 |  | 0.5
EAMozambiqueMDRMZ026 | ea | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | Achieved Late | 2025-01-15 00:00:00 | -17 |  | 0.5
EAComorosMDRKM013 | ea | procurement_and_logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Achieved Late | 2025-02-15 00:00:00 | -55 |  | 0.5
EAComorosMDRKM013 | ea | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Achieved Late | 2025-03-15 00:00:00 | -79 |  | 0.5
EAComorosMDRKM013 | ea | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | Not Achieved | - | -365 |  | 0.5
EAMadagascarMDRMG023 | ea | procurement_and_logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | DNU | - |  |  | 0.5
EAMadagascarMDRMG023 | ea | procurement_and_logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | DNU | - |  |  | 0.5
EAMadagascarMDRMG023 | ea | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | DNU | - |  |  | 0.5
EAVanuatuMDRVU012 | ea | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Achieved Early | 2024-12-17 00:00:00 | 1 | Not Escalated | 0.5
EAVanuatuMDRVU012 | ea | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-12-17 00:00:00 | 2 | Not Escalated | 0.5
EAVanuatuMDRVU012 | ea | surge | Identification of 1st RR personnel within 48h of the 1st alert | Achieved Early | 2024-12-19 00:00:00 | 1 | Not Escalated | 0.5
EAUgandaMDRUG055 | ea | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Not Achieved | - | -365 | Not Escalated | 0.5
EAUgandaMDRUG055 | ea | surge | RR personnel Alert sent within 12h of the request | Achieved Late | 2025-03-03 00:00:00 | -12 | Not Escalated | 0.5
EAUgandaMDRUG055 | ea | surge | Identification of 1st RR personnel within 48h of the 1st alert | Achieved Late | 2025-03-03 00:00:00 | -11 | Not Escalated | 0.5
EAMalawiMDRMW021 | ea | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Not Achieved | - | -365 |  | 0.5
EAMalawiMDRMW021 | ea | surge | RR personnel Alert sent within 12h of the request | Not Achieved | - | -365 |  | 0.5
EAMalawiMDRMW021 | ea | surge | Identification of 1st RR personnel within 48h of the 1st alert | Not Achieved | - | -365 |  | 0.5
EAMozambiqueMDRMZ026 | ea | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Not Achieved | - | -365 |  | 0.5
EAMozambiqueMDRMZ026 | ea | surge | RR personnel Alert sent within 12h of the request | Not Achieved | - | -365 |  | 0.5
EAMozambiqueMDRMZ026 | ea | surge | Identification of 1st RR personnel within 48h of the 1st alert | Not Achieved | - | -365 |  | 0.5
EAComorosMDRKM013 | ea | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Not Achieved | - | -365 |  | 0.5
EAComorosMDRKM013 | ea | surge | RR personnel Alert sent within 12h of the request | Not Achieved | - | -365 |  | 0.5
EAComorosMDRKM013 | ea | surge | Identification of 1st RR personnel within 48h of the 1st alert | Not Achieved | - | -365 |  | 0.5
EAMadagascarMDRMG023 | ea | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | DNU | - |  |  | 0.5
EAMadagascarMDRMG023 | ea | surge | RR personnel Alert sent within 12h of the request | DNU | - |  |  | 0.5
EAMadagascarMDRMG023 | ea | surge | Identification of 1st RR personnel within 48h of the 1st alert | DNU | - |  |  | 0.5
DREFMozambiqueMDRMZ026 | dref | assessment | Initial needs assessments completed within 72 hours​ of the event. | Not Achieved | - | -365 | Not Escalated
DREFMozambiqueMDRMZ026 | dref | financial_management | Project funding agreements (PFAs) signed by the NS and the IFRC no longer than 7 days from the DREF approval | Not Achieved | - | -365 | Not Escalated
DREFMozambiqueMDRMZ026 | dref | financial_management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF approval | Not Achieved | - | -365 | Not Escalated
DREFMozambiqueMDRMZ026 | dref | financial_management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Not Achieved | - | -365 | Not Escalated
DREFMozambiqueMDRMZ026 | dref | financial_management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Not Achieved | - | -365 | Not Escalated
DREFMozambiqueMDRMZ026 | dref | planning_and_resource_mobilization | DREF approved within 10 days of the trigger. 14 if the NS has started responding. | Achieved Early | 2024-12-17 | 8 | Not Escalated | 1
DREFMozambiqueMDRMZ026 | dref | planning_and_resource_mobilization | Approval by the DREF appeal manager within 24h of receiving the final package | Achieved Early | 2024-12-17 | 12 | Not Escalated | 1
DREFMozambiqueMDRMZ026 | dref | procurement_and_logistics | Supply chain plan developed within 1 week of DREF approval | Achieved Early | 2024-12-16 | 18 | Not Escalated | 1
DREFMozambiqueMDRMZ026 | dref | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Not Achieved | - | -365 | Not Escalated
DREFMozambiqueMDRMZ026 | dref | programme_delivery | First round of payment received to the target beneficiaries four weeks after the DREF approval - 1 Month (Date) | Not Achieved | - | -365 | Not Escalated
DREFMozambiqueMDRMZ026 | dref | risk_and_accountability | Risk management one pager using country risk the dashboard developed within 48h after the approval | Achieved Early | 2024-12-18 | 9 | Not Escalated | 1
DREFMozambiqueMDRMZ026 | dref | risk_and_accountability | Project manager and appeal manager responsibilities one pager is shared with approval (max 14 days after trigger) | Achieved Early | 2024-12-18 | 11 | Not Escalated | 1
DREFMozambiqueMDRMZ026 | dref | surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster (if relevant) | Achieved Early | 2024-12-15 | 1 | Not Escalated | 1
DREFMozambiqueMDRMZ026 | dref | surge | RR personnel Alert sent within 12h of the request | Achieved Early | 2024-12-15 | 2 | Not Escalated | 1
DREFMozambiqueMDRMZ026 | dref | surge | Identification of 1st RR personnel within 48h of the 1st alert | Achieved Early | 2024-12-18 | 0 | Not Escalated | 1
MCMRMDRS1005 | mcmr | coordination | Establish a Multi country coordination mechanimsms with the membership for the crisis | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | financial_management | A breakdown of the Financial allocation per country is made within 5 days of the approval of the EA | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | financial_management | Transferts to NS & IFRC Sec. Structure are made within 5 days of the allocation table | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | hr_planning_and_recruitement | Key initial longer-term positions (for the Regional/multi country level) identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | hr_planning_and_recruitement | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | information_management | A multi country IM Snapshot is in place and updated timely to display the situation and the activities being implemented | Missing | - |  | Not Escalated | 0
MCMRMDRS1005 | mcmr | planning_and_resource_mobilization | Disaster Brief done for the Management Call to inform the FAD between 48-72 h | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | planning_and_resource_mobilization | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | planning_and_resource_mobilization | Operational Strategy validated 12 days after the EA | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | planning_and_resource_mobilization | Supply chain plan developed for the regional needs between logs and ops within 1 week of the approved EA | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | procurement_and_logistics | Supply chain plan developed for the regional needs between logs and ops within 1 week of the approved EA | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | procurement_and_logistics | Fully approved and submitted multi country requisitions for NFIs within 1 week of the EA (when relevant) | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | procurement_and_logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | surge | Regional RR personnel Alert sent within 12h of the request | Not Achieved | - | -365 | Not Escalated
MCMRMDRS1005 | mcmr | surge | Identification of 1st RR personnel within 48h of the 1st alert | Not Achieved | - | -365 | Not Escalated