## EA_MD
Ref | tracker Status | Trigger Date | Region | Country | ISO | Appeal Code | Appeal Name | Disaster Type | Classification | EWTS Varient | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Disaster Brief done to inform the FAD between 48-72 h | Approval of decision for DREF operation escalation to EA (disaster trigger date) | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Operational Strategy validated 7 days after the EA | Escalation | % coverage of the EA - 10 days (Sect.) | % coverage of the EA - 2 weeks (Sect.) | % coverage of the EA - 3 weeks (Sect.) | % coverage of the EA - 1 month (Sect.) | % coverage of the EA - 2 months (Sect.) | % coverage of the EA - 3 months (Sect.) | % coverage of the EA - 10 days (Fed.) | % coverage of the EA - 2 weeks (Fed.) | % coverage of the EA - 3 weeks (Fed.) | % coverage of the EA - 1 month (Fed.) | % coverage of the EA - 2 months (Fed.) | % coverage of the EA - 3 months (Fed.) | A resource mobilization plan is developed and approved within 2 weeks of the EA | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | RR personnel Alert sent within 12h of the request | Identification of 1st rotation RR personnel within 48h of the alert | % of female and male out of the RRP deployed - 2 weeks | % of female and male out of the RRP deployed - 1 month | % of female and male out of the RRP deployed - 2 months | % of female and male out of the RRP deployed - 3 months | % of RRP coming within the region of the disaster - 2 weeks | % of RRP coming within the region of the disaster - 1 Month | % of RRP coming within the region of the disaster - 2 months | % of RRP coming within the region of the disaster - 3 months | # of RR deployed arriving in country of operation within 4 days from deployment message - 1 Week | # of RR deployed arriving in country of operation within 4 days from deployment message - 2 Weeks | # of RR deployed arriving in country of operation within 4 days from deployment message - 1 month | # of RR deployed arriving in country of operation within 4 days from deployment message - 2 months | # of RR deployed arriving in country of operation within 4 days from deployment message - 3 months | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Hold a mini summit within 48 h of the disaster | The Movement Joint statement is produced 48h after the Mini Summit | review/adapt membership coordination for the context for this specific emergency | Appropriate membership coordination is in place after 24h of disaster | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 week) | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 month) | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | First round of payment received to the target beneficiaries four weeks after the EA launch for sudden onset (when relevant and when CVA is planned) | NFIs distributed to targetted population within one month of the disaster - 1 month (Date) | NFIs distributed to targetted population within one month of the disaster - 2 months (%) | NFIs distributed to targetted population within one month of the disaster - 3 months (%) | % of targeted population receiving assistance - 2 weeks | % of targeted population receiving assistance - 1 Month | % of targeted population receiving assistance - 2 months | % of targeted population receiving assistance - 3 months | % implementation rate of available budget - 2 weeks | % implementation rate of available budget - 3 weeks | % implementation rate of available budget - 1 month | % implementation rate of available budget - 2 months | % implementation rate of available budget - 3 months | Operation is MSR (v.2021) compliant | If the country is not MSR, enough resource (HR/Funds) have been allocated to operate in a Red/orange security phase areas
EAMozambiqueMDRM989 | Not Active | 2024-06-20 | Africa | Mozambique |  | MDRM989 | Mozambique earthquake (MDRM989) | Earthquake | Orange | Emergency Appeal | 2024-06-24 | 2024-06-26 | DNU | 2024-06-28 | 2024-07-03 | No | 44% | 60% | 80% | 82% | 82% | 82% | 31% | 40% | 60% | 66% | 69% | 69% | 2024-07-10 | 2024-06-21 | 2024-06-21 | 2024-06-22 | 50% | 40% | 40% | 50% | 90% | 90% | 90% | 90% | 1 | 1 | 3 | 3 | 2 | 2024-07-01 | 2024-07-02 | DNU | DNU | 2024-07-05 | 2024-06-22 | 2024-07-05 | - | - | - | - | 2024-07-05 | 2024-07-19 | 2024-08-10 | 2024-07-04 | 2024-07-07 | 2024-07-10 | 2024-07-12 | - | 2024-07-18 | 60% | 100% | 40% | 60% | 60% | 70% | 30% | 35% | 40% | 50% | 60% | 2024-06-25 | -
EANigeriaMDRN777 | Not Active | 2024-07-15 | Africa | Nigeria |  | MDRN777 | Nigeria population movement (MDRN777) | Population Movement | Red | Emergency Appeal | 2024-07-17 | NA | DNU | 2024-07-22 | 2024-07-30 | No | 50% | 70% | 103% | 103% | - | - | 20% | 31% | 40% | 50% | - | - | 2024-08-15 | 2024-07-18 | 2024-07-18 | 2024-07-20 | 70% | 70% | 80% | 80% | 80% | 70% | 80% | 80% | 0 | 0 | 2 | 5 | 4 | 2024-07-29 | 2024-07-30 | DNU | DNU | 2024-07-29 | 2024-07-16 | 2024-07-29 | 2024-07-30 | 2024-08-02 | - | - | - | - | - | 2024-07-30 | 2024-08-02 | 2024-08-03 | 2024-08-06 | - | 2024-08-12 | 50% | 70% | 50% | 55% | 56% | 65% | 20% | 30% | 40% | 60% | 70% | 2024-07-22 | -
EAPeruMDRO999 | Active | 2024-08-11 | Americas | Peru |  | MDRO999 | Peru population movement (MDRO999) | Population Movement | Orange | Emergency Appeal | 2024-08-13 | 2024-08-20 | DNU | 2024-08-21 | 2024-08-29 | No | 40% | 50% | 90% | 105% | 106% | - | 20% | 32% | 45% | 48% | 54% | - | 2024-09-20 | 2024-08-15 | 2024-08-11 | 2024-08-13 | 90% | 90% | 90% | 90% | 60% | 80% | 80% | 90% | 0 | 0 | 3 | 3 | 3 | 2024-08-30 | 2024-09-01 | 2024-08-13 | 2024-08-15 | 2024-08-28 | 2024-08-11 | 2024-08-28 | 2024-08-27 | 2024-08-29 | 2024-08-25 | 2024-08-30 |  |  | - | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-09-01 | 2024-09-20 | 2024-09-11 | 70% | 100% | 60% | 63% | 68% | 72% | 30% | 35% | 45% | 70% | 90% | - | 2024-08-15
EAMaldivesMDRM787 | Active | 2024-08-28 | Asia | Maldives |  | MDRM787 | Maldives floods (MDRM787) | Flood | Orange | Emergency Appeal | 2024-09-01 | NA | DNU | 2024-09-06 | 2024-09-12 | No | 20% | 40% | 70% | 90% | 92% | 100% | 10% | 20% | 42% | 66% | 70% | 72% | 2024-09-25 | 2024-09-01 | 2024-08-29 | 2024-08-30 | 30% | 35% | 40% | 50% | 90% | 90% | 90% | 95% | 0 | 1 | 2 | 2 | 1 | 2024-09-15 | 2024-09-18 | 2024-09-01 | 2024-09-02 | 2024-09-15 | 2024-08-29 | 2024-09-15 | 2024-09-16 | 2024-09-20 | 2024-08-29 | 2024-09-01 | 2024-09-09 | 2024-09-20 | 2024-09-30 | 2024-09-14 | 2024-09-20 | 2024-09-22 | 2024-09-25 | 2024-10-01 | 2024-09-25 | 80% | 90% | 50% | 60% | 62% | 68% | 50% | 55% | 70% | 90% | 100% | - | 2024-09-03
EAJordanMDRJ000 | Active | 2024-09-01 | MENA | Jordan |  | MDRJ000 | Jordan earthquake (MDRJ000) | Earthquake | Red | Emergency Appeal | 2024-09-09 | NA | DNU | 2024-09-12 | 2024-09-22 | Yes | 20% | 30% | 40% | - | - | - | 20% | 30% | 30% | - | - | - | 2024-10-15 | 2024-09-06 | 2024-09-05 | 2024-09-05 | 20% | 40% | 40% | 30% | 40% | 45% | 45% | 50% | 1 | 3 | 3 | 5 | 2 | 2024-09-21 | 2024-09-25 | NA | NA | 2024-09-21 | 2024-09-04 | 2024-09-20 | - | - | - | - | - | - | - | 2024-09-21 | 2024-09-23 | 2024-09-28 | 2024-10-01 | 2024-10-12 | 2024-10-04 | 40% | 45% | 50% | 55% | 55% | 57% | 25% | 40% | 55% | 56% | - | - | 2024-09-15
2

## DREF_MD
Ref | tracker Status | Trigger Date | Region | Country | ISO | Appeal Code | Appeal Name | Disaster Type | Classification | EWTS Varient | Escalation | Initial needs assessments completed within 72 hours​ of the event. | Risk management one pager using country risk the dashboard developed within 48h after the approval | Project manager and appeal manager responsibilities one pager is shared with approval (max 14 days after trigger) | DREF approved within 10 days of the trigger. 14 if the NS has started responding. | Approval by the DREF appeal manager within 24h of receiving the final package | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster (if relevant) | RR personnel Alert sent within 12h of the request | Identification of 1st rotation RR personnel within 48h of the alert | % of female and male out of the RRP deployed - 2 weeks | % of female and male out of the RRP deployed - 1 month | % of female and male out of the RRP deployed - 2 months | % of female and male out of the RRP deployed - 3 months | % of RRP coming within the region of the disaster - 2 weeks | % of RRP coming within the region of the disaster - 1 Month | % of RRP coming within the region of the disaster - 2 months | % of RRP coming within the region of the disaster - 3 months | # of RR deployed arriving in country of operation within 4 days from deployment message - 1 Week | # of RR deployed arriving in country of operation within 4 days from deployment message - 2 Weeks | # of RR deployed arriving in country of operation within 4 days from deployment message - 1 month | # of RR deployed arriving in country of operation within 4 days from deployment message - 2 months | # of RR deployed arriving in country of operation within 4 days from deployment message - 3 months | Supply chain plan developed within 1 week of DREF approval | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Project funding agreements (PFAs) signed by the NS and the IFRC no longer than 7 days from the DREF approval | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF approval | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | First round of payment received to the target beneficiaries four weeks after the DREF approval - 1 Month (Date) | First round of payment received to the target beneficiaries four weeks after the DREF approval l - 2 Months (%) | First round of payment received to the target beneficiaries four weeks after the DREF approval - 3 Month (%) | % of targeted population receiving assistance - 2 weeks | % of targeted population receiving assistance - 1 Month | % of targeted population receiving assistance - 2 Months | % of targeted population receiving assistance - 3 months | EHI distributed to targetted population on time - 1 month | EHI distributed to targetted population on time - 2 months | EHI distributed to targetted population on time - 3 months | Implementation rate: 30% after 1 month | Implementation rate: | Implementation rate: 2 | Operation is MSR (v.2021) compliant | If the country is not MSR, enough resource (HR/ Funds) have been allocated to operate in a Red/ orange security phase areas
DREFAfghanistanMDRA111 | active | 2024-06-05 | Asia | Afghanistan | AFG | MDRA111 | Afghanistan Civil Unrest (MDRA111) | Civil Unrest | Red | DREF | No | 2024-06-07 | 2024-06-06 | 2024-06-09 | 2024-06-15 | 2024-06-05 | 2024-06-06 | 2024-06-06 | 2024-06-09 | 60% | 70% | 70% | 50% | 90% | 90% | 80% | 80% | 2 | 2 | 3 | 3 | 2 | 2024-06-21 | 2024-06-22 | 2024-06-20 | 2024-06-22 | 2024-06-23 | 2024-06-26 | 2024-06-15 | 40% | 60% | 50% | 60% | 62% | 68% | 55% | 60% | 70% | 30% | 50% | 70% | 2024-06-06 | -
DREFBangladeshMDRB567 | not active | 2024-07-01 | Asia | Bangladesh | BGD | MDRB567 | Bangladesh Cyclone (MDRB567) | Cyclone | Orange | DREF | No | 2024-07-02 | 2024-07-02 | 2024-07-12 | 2024-07-12 | 2024-07-03 | 2024-07-02 | 2024-07-02 | 2024-07-05 | 70% | 70% | 90% | 90% | 85% | 70% | 85% | 85% | 0 | 0 | 1 | 4 | 4 | 2024-07-18 | 2024-07-14 | 2024-07-19 | 2024-07-22 | 2024-07-24 | 2024-07-27 | 2024-07-12 | 60% | 90% | 50% | 63% | 72% | 85% | 40% | 43% | 55% | 25% | 55% | 60% | 2024-07-02 | -
DREFGermanyMDRG909 | active | 2024-08-10 | Europe | Germany | DEU | MDRG909 | Germany Earthquake (MDRG909) | Earthquake | Orange | DREF | No | 2024-08-14 | 2024-08-12 | 2024-08-20 | 2024-08-21 | 2024-08-11 | 2024-08-11 | 2024-08-11 | 2024-08-13 | 85% | 90% | 90% | 90% | 50% | 80% | 80% | 90% | 0 | 0 | 2 | 3 | 3 | 2024-08-29 | 2024-09-02 | 2024-08-30 | 2024-09-02 | 2024-09-03 | 2024-09-06 | 2024-08-21 | 90% | 92% | 35% | 63% | 68% | 72% | 70% | 72% | 80% | 40% | 60% | 80% | 2024-08-12 | -
DREFChileMDRC464 | active | 2024-08-20 | Americas | Chile | CHL | MDRC464 | Chile Fire (MDRC464) | Fire | Red | DREF | No | 2024-08-25 | 2024-09-03 | 2024-08-25 | 2024-08-30 | 2024-08-23 | 2024-08-22 | 2024-08-21 | 2024-08-23 | 30% | 40% | 40% | 50% | 90% | 90% | 95% | 95% | 0 | 1 | 2 | 2 | 2 | 2024-09-07 | 2024-09-02 | 2024-09-08 | 2024-09-10 | 2024-09-11 | 2024-09-15 | 2024-08-30 | 30% | 65% | 40% | 60% | 60% | 70% | 72% | 74% | 85% | 45% | 64% | 100% | 2024-08-21 | -
DREFEgyptMDRE698 | not active | 2024-09-02 | MENA | Egypt | EGY | MDRE698 | Egypt Cyclone (MDRE698) | Cyclone | Orange | DREF | No | 2024-09-03 | 2024-09-23 | 2024-09-21 | 2024-09-18 | 2024-09-08 | 2024-09-05 | 2024-09-03 | 2024-09-15 | 85% | 85% | 100% | 100% | 90% | 95% | 95% | 95% | 1 | 8 | 12 | 11 | 11 | 2024-09-25 | 2024-09-14 | 2024-09-22 | 2024-09-25 | 2024-09-26 | 2024-09-29 | 2024-09-18 | 45% | 70% | 60% | 60% | 70% | 75% | 80% | 90% | 90% | 70% | 100% | - | - | 2024-09-12

## MCMR_MD
Ref | tracker Status | Disaster Escalation Date | Region | Country | ISO | Appeal Code | Appeal Name | Disaster Type | Classification | EWTS Varient | Escalation | Disaster Brief done for the Management Call to inform the FAD between 48-72 h | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Operational Strategy validated 12 days after the EA | % (Total Fed and Sec) coverage of the EA - 10 days | % (Total Fed and Sec)coverage of the EA - 2 weeks | % (Total Fed and Sec)coverage of the EA - 3 weeks | % (Total Fed and Sec)coverage of the EA - 1 month | % (Total Fed and Sec)coverage of the EA - 2 months | % (Total Fed and Sec)coverage of the EA - 3 months | Regional RR personnel Alert sent within 12h of the request | Identification of 1st rotation RR personnel within 48h of the alert | % of female and male out of the RRP deployed - 2 weeks | % of female and male out of the RRP deployed - 1 month | % of female and male out of the RRP deployed - 2 months | % of female and male out of the RRP deployed - 3 months | % of RRP coming within the region of the disaster - 2 weeks | % of RRP coming within the region of the disaster - 1 Month | % of RRP coming within the region of the disaster - 2 months | % of RRP coming within the region of the disaster - 3 months | # of RR deployed arriving in country of operation within 4 days from deployment message - 1 Week | # of RR deployed arriving in country of operation within 4 days from deployment message - 2 Weeks | # of RR deployed arriving in country of operation within 4 days from deployment message - 1 month | # of RR deployed arriving in country of operation within 4 days from deployment message - 2 months | # of RR deployed arriving in country of operation within 4 days from deployment message - 3 months | Key initial longer-term positions (for the Regional/multi country level) identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Establish a Multi country coordination mechanimsms with the membership for the crisis (24 hours since escalation date) | Supply chain plan developed for the regional needs between logs and ops within 1 week of the approved EA | Fully approved and submitted multi country requisitions for NFIs within 1 week of the EA (when relevant) | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | A multi country dashboard is in place and updated timely to display the situation and the activities being implemented | A breakdown of the Financial allocation per country is made within 5 days of the approval of the EA | Transferts to NS & IFRC Sec. Structure are made within 5 days of the allocation table | Cumulated % of targeted population receiving assistance | Cumulated % implementation rate of available budget
MCMRNepalMDRS2002 | active | 2024-06-10 | Asia | Nepal | NPL | MDRS2002 | Earthquake Minu South Asia (MDRS2002) | Earthquake | Orange | Multi Country | No | 2024-06-21 | 2024-06-22 | 2024-06-29 | 40% | 50% | 90% | 90% | 90% | - | 2024-06-11 | 2024-06-13 | 70% | 70% | 80% | 80% | 80% | 70% | 80% | 80% | 0 | 2 | 4 | 4 | 4 | 2024-06-29 | 2024-06-30 | 2024-06-11 | 2024-06-28 | 2024-06-30 | 2024-07-03 | - | 2024-06-27 | 2024-06-30 | 70% | 90%
MCMRZambiaMDRS7890 | active | 2024-07-11 | Africa | Zambia | ZMB | MDRS7890 | Covid 19 Africa (MDRS7890) | Epidemic | Orange | Multi Country | No | 2024-07-14 | 2024-07-14 | 2024-07-30 | 20% | 40% | 70% | - | - | - | 2024-07-12 | 2024-07-15 | 90% | 90% | 90% | 90% | 60% | 80% | 80% | 90% | 1 | 2 | 5 | 4 | 4 | 2024-07-19 | 2024-07-22 | 2024-07-12 | 2024-07-17 | 2024-07-19 | 2024-07-23 | - | 2024-07-19 | 2024-07-25 | 60% | 85%
MCMRJordanMDRS1234 | not active | 2024-08-15 | MENA | Jordan | JOR | MDRS1234 | Civil waR MENA (MDRS1234) | Civil Unrest | Red | Multi Country | No | 2024-08-18 | 2024-08-19 | 2024-09-01 | 60% | 70% | 72% | 75% | 78% | 78% | 2024-08-17 | 2024-08-20 | 30% | 35% | 40% | 50% | 90% | 90% | 90% | 95% | 0 | 2 | 3 | 2 | 2 | 2024-08-25 | 2024-08-28 | 2024-08-18 | 2024-08-26 | 2024-08-25 | 2024-08-27 | 2024-08-22 | 2024-08-24 | 2024-08-29 | 75% | 103%

## Protracted_MD
Ref | tracker Status | Escalation date | Region | Country | ISO | Appeal Code | Appeal Name | Disaster Type | Classification | EWTS Varient | Escalation | Needs assessments of triggers to identify the need for an EA. (before EA launch) | Disaster Brief done for the Management Call to inform the FAD between 48-72 | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | Operational Strategy validated 10 to 14 days after the EA | % coverage of the EA - 10 days | % coverage of the EA - 2 weeks | % coverage of the EA - 3 weeks | % coverage of the EA - 1 month | % coverage of the EA - 2 months | % coverage of the EA - 3 months | A resource mobilization plan is developed and approved within 3 to 4 weeks of the EA that looks at long term funding and sustianability. | IFRC advocates with NS for the approval and use of Surge or in country capacity from movement partners within the first 5 days of the trigger | RR personnel Alert sent within 12h of the request | Identification of 1st rotation RR personnel within 5 days of the alert *if not aligned to readiness process could be slower | % of female and male out of the RRP deployed - 2 weeks | % of female and male out of the RRP deployed - 1 month | % of female and male out of the RRP deployed - 2 months | % of female and male out of the RRP deployed - 3 months | % of RRPs with 3 months deployments | % of RRP coming within the region of the disaster - 2 weeks | % of RRP coming within the region of the disaster - 1 Month | % of RRP coming within the region of the disaster - 2 months | % of RRP coming within the region of the disaster - 3 months | # of RR deployed arriving in country of operation within 4 days from deployment message - 1 Week | # of RR deployed arriving in country of operation within 4 days from deployment message - 2 Weeks | # of RR deployed arriving in country of operation within 4 days from deployment message - 1 month | # of RR deployed arriving in country of operation within 4 days from deployment message - 2 months | # of RR deployed arriving in country of operation within 4 days from deployment message - 3 months | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Hold a mini summit within 48 h of the disaster | Review/adapt membership coordination framework for the context for this specific emergency | Ensure an appropriate membership coordination framework is in place after 24h of trigger | Initial supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | A dashboard is in place and updated timely to display the situation and the activities being implemented (24h) | A dashboard is in place and updated timely to display the situation and the activities being implemented (72h) | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 week) | A dashboard is in place and updated timely to display the situation and the activities being implemented (2 weeks) | A dashboard is in place and updated timely to display the situation and the activities being implemented (1 m) | Project agreements signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | After PA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | First round of payment received to the target beneficiaries four weeks after the EA launch for sudden onset (when relevant and when CVA is planned) | NFIs distributed to targetted population within one month of the EA | % of targeted population receiving assistance | % implementation rate of available budget | Operation is MSR (v.2021) compliant | If the country is not MSR, enough resource (HR/Funds) have been allocated to operate in a Red/orange security phase areas
PCCEIraqMDRI1998 | active | 2024-07-06 | MENA | Iraq | IRQ | MDRI1998 | Iraq complex emergency (MDRI1998) | Complex Emergency | Red | Protracted | No | 2024-06-06 | 2024-07-09 | 2024-07-06 | 2024-07-16 | 70% | 80% | 106% | 106% | 107% | 107% | 2024-08-02 | 2024-07-10 | 2024-07-07 | 2024-07-11 | 40% | 40% | 60% | 60% | 30% | 90% | 90% | 94% | 95% | 0 | 2 | 5 | 5 | 3 | 2024-07-12 | 2024-07-14 | 2024-07-08 | 2024-07-08 | 2024-07-07 | 2024-07-13 | - | - | - | - | - | - | - | 2024-07-14 | 2024-07-17 | 2024-07-18 | 2024-07-21 | 2024-08-02 | 2024-08-03 | 70% | 80% | 2024-07-14 | -
PCCENigeriaMDRN6879 | not active | 2024-08-10 | Africa | Nigeria | NGA | MDRN6879 | Nigeria population movement (MDRN6879) | Population Movement | Orange | Protracted | No | 2024-07-20 | 2024-08-13 | 2024-08-10 | 2024-08-19 | 70% | 90% | 92% | 96% | 98% | 100% | 2024-09-01 | 2024-08-14 | 2024-08-11 | 2024-08-16 | 30% | 40% | 40% | 20% | 30% | 80% | 84% | 90% | 95% | 0 | 1 | 2 | 2 | 0 | 2024-08-18 | 2024-08-21 | 2024-08-13 | 2024-08-12 | 2024-08-11 | 2024-08-19 | 2024-08-18 | 2024-08-21 | 2024-08-25 | 2024-08-25 | 2024-08-29 | 2024-08-04 | - | 2024-08-20 | 2024-08-23 | 2024-08-25 | 2024-08-29 | 2024-08-10 | 2024-08-11 | 80% | 85% | 2024-08-20 | -

## Lists
Region | Country | iso | iso3 | Disaster Type | Classification | EWTS Varient
Africa | Afghanistan | AF | AFG | Biological Emergency | Yellow | Emergency Appeal
Asia | Albania | AL | ALB | Chemical Emergency | Orange | DREF
Americas | Algeria | DZ | DZA | Civil Unrest | Red | Multi Country
Europe | American Samoa | AS | ASM | Cold Wave |  | Multi Regional
MENA | Andorra | AD | AND | Complex Emergency |  | Protracted
Global | Angola | AO | AGO | Cyclone
| Antigua and Barbuda | AG | ATG | Drought
| Argentina | AR | ARG | Earthquake
| Armenia | AM | ARM | Epidemic
| Australia | AU | AUS | Fire
| Austria | AT | AUT | Flood
| Azerbaijan | AZ | AZE | Food Insecurity
| Bahamas | BS | BHS | Heat Wave
| Bahrain | BH | BHR | Insect Infestation
| Bangladesh | BD | BGD | Landslide
| Barbados | BB | BRB | Other
| Belarus | BY | BLR | Pluvial/Flash Flood
| Belgium | BE | BEL | Population Movement
| Belize | BZ | BLZ | Radiological Emergency
| Benin | BJ | BEN | Storm Surge
| Bhutan | BT | BTN | Transport Accident
| Bolivia | BO | BOL | Transport Emergency
| Bosnia and Herzegovina | BA | BIH | Tsunami
| Botswana | BW | BWA | Volcanic Eruption
| Bouvet Island | BV | BVT
| Brazil | BR | BRA
| British Indian Ocean Territory | IO | IOT
| British Virgin Islands | VG | VGB
| Brunei Darussalam | BN | BRN
| Bulgaria | BG | BGR
| Burkina Faso | BF | BFA
| Burundi | BI | BDI
| Cabo Verde | CV | CPV
| Cambodia | KH | KHM
| Cameroon | CM | CMR
| Canada | CA | CAN
| Cayman Islands | KY | CYM
| Central African Republic | CF | CAF
| Chad | TD | TCD
| Chile | CL | CHL
| China | CN | CHN
| Christmas Island | CX | CXR
| Cocos (Keeling) Islands | CC | CCK
| Colombia | CO | COL
| Comoros | KM | COM
| Congo | CG | COG
| Cook Islands | CK | COK
| Costa Rica | CR | CRI
| Croatia | HR | HRV
| Cuba | CU | CUB
| Cyprus | CY | CYP
| Czech Republic | CZ | CZE
| Côte d'Ivoire | CI | CIV
| Democratic People's Republic of Korea | KP | PRK
| Democratic Republic of Congo | CD | COD
| Denmark | DK | DNK
| Djibouti | DJ | DJI
| Dominica | DM | DMA
| Dominican Republic | DO | DOM
| Ecuador | EC | ECU
| Egypt | EG | EGY
| El Salvador | SV | SLV
| Equatorial Guinea | GQ | GNQ
| Eritrea | ER | ERI
| Estonia | EE | EST
| Eswatini, Kingdom of | SZ | SWZ
| Ethiopia | ET | ETH
| Falkland Islands (Malvinas) | FK | FLK
| Faroe Islands | FO | FRO
| Fiji | FJ | FJI
| Finland | FI | FIN
| France | FR | FRA
| Gabon | GA | GAB
| Gambia, Republic of The | GM | GMB
| Georgia | GE | GEO
| Germany | DE | DEU
| Ghana | GH | GHA
| Greece | GR | GRC
| Greenland | GL | GRL
| Grenada | GD | GRD
| Guam | GU | GUM
| Guatemala | GT | GTM
| Guernsey | GG | GGY
| Guinea | GN | GIN
| Guinea-Bissau | GW | GNB
| Guyana | GY | GUY
| Haiti | HT | HTI
| Heard Island and McDonald Islands | HM | HMD
| Honduras | HN | HND
| Hungary | HU | HUN
| Iceland | IS | ISL
| India | IN | IND
| Indonesia | ID | IDN
| Iran, Islamic Republic of | IR | IRN
| Iraq | IQ | IRQ
| Ireland | IE | IRL
| Isle of Man | IM | IMN
| Israel | IL | ISR
| Italy | IT | ITA
| Jamaica | JM | JAM
| Japan | JP | JPN
| Jersey | JE | JEY
| Jordan | JO | JOR
| Kazakhstan | KZ | KAZ
| Kenya | KE | KEN
| Kiribati | KI | KIR
| Kosovo | XK | XKX
| Kuwait | KW | KWT
| Kyrgyzstan | KG | KGZ
| Lao People's Democratic Republic | LA | LAO
| Latvia | LV | LVA
| Lebanon | LB | LBN
| Lesotho | LS | LSO
| Liberia | LR | LBR
| Libya | LY | LBY
| Liechtenstein | LI | LIE
| Lithuania | LT | LTU
| Luxembourg | LU | LUX
| Madagascar | MG | MDG
| Malawi | MW | MWI
| Malaysia | MY | MYS
| Maldives | MV | MDV
| Mali | ML | MLI
| Malta | MT | MLT
| Marshall Islands | MH | MHL
| Mauritania | MR | MRT
| Mauritius | MU | MUS
| Mexico | MX | MEX
| Micronesia, Federated States of | FM | FSM
| Moldova, Republic of | MD | MDA
| Monaco | MC | MCO
| Mongolia | MN | MNG
| Montenegro | ME | MNE
| Montserrat | MS | MSR
| Morocco | MA | MAR
| Mozambique | MZ | MOZ
| Myanmar | MM | MMR
| Namibia | NA | NAM
| Nepal | NP | NPL
| Netherlands | NL | NLD
| New Zealand | NZ | NZL
| Nicaragua | NI | NIC
| Niger | NE | NER
| Nigeria | NG | NGA
| Norfolk Island | NF | NFK
| North Macedonia | MK | MKD
| Northern Mariana Islands | MP | MNP
| Norway | NO | NOR
| Pakistan | PK | PAK
| Palau | PW | PLW
| Palestine | PS | PSE
| Panama | PA | PAN
| Papua New Guinea | PG | PNG
| Paraguay | PY | PRY
| Peru | PE | PER
| Philippines | PH | PHL
| Poland | PL | POL
| Portugal | PT | PRT
| Qatar | QA | QAT
| Republic of Korea | KR | KOR
| Romania | RO | ROU
| Russian Federation | RU | RUS
| Rwanda | RW | RWA
| Saint Kitts and Nevis | KN | KNA
| Saint Lucia | LC | LCA
| Saint Vincent and the Grenadines | VC | VCT
| Samoa | WS | WSM
| San Marino | SM | SMR
| Sao Tome and Principe | ST | STP
| Saudi Arabia | SA | SAU
| Senegal | SN | SEN
| Serbia | RS | SRB
| Seychelles | SC | SYC
| Sierra Leone | SL | SLE
| Singapore | SG | SGP
| Slovakia | SK | SVK
| Slovenia | SI | SVN
| Solomon Islands | SB | SLB
| Somalia | SO | SOM
| South Africa | ZA | ZAF
| South Georgia and the South Sandwich Island | GS | SGS
| South Sudan | SS | SSD
| Spain | ES | ESP
| Sri Lanka | LK | LKA
| Sudan | SD | SDN
| Suriname | SR | SUR
| Sweden | SE | SWE
| Switzerland | CH | CHE
| Syrian Arab Republic | SY | SYR
| Tajikistan | TJ | TJK
| Tanzania, United Republic of | TZ | TZA
| Thailand | TH | THA
| Timor-Leste | TL | TLS
| Togo | TG | TGO
| Tokelau | TK | TKL
| Tonga | TO | TON
| Trinidad and Tobago | TT | TTO
| Tunisia | TN | TUN
| Turkmenistan | TM | TKM
| Turks and Caicos islands | TC | TCA
| Tuvalu | TV | TUV
| Türkiye | TR | TUR
| Uganda | UG | UGA
| Ukraine | UA | UKR
| United Arab Emirates | AE | ARE
| United Kingdom | GB | GBR
| United States | US | USA
| United States Virgin Islands | VI | VIR
| Uruguay | UY | URY
| Uzbekistan | UZ | UZB
| Vanuatu | VU | VUT
| Venezuela | VE | VEN
| Viet Nam | VN | VNM
| Yemen | YE | YEM
| Zambia | ZM | ZMB
| Zimbabwe | ZW | ZWE

## Time frames and targets
EA Varient |  |  |  |  | DREF Varient |  |  |  |  | MCMR Varient |  |  |  |  | Protracted crisis varient
Area | Indicator | Indicator (short) | Expected date for completion (from disaster trigger date) | Other targets | Area | Indicator | Indicator (short) | Expected date for completion (from disaster trigger date) | Other targets | Assessment ​ | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Initial needs assessment | Expected date for completion (from disaster trigger date) | Other targets | Area | Indicator | Indicator (short) | Expected date for completion (from disaster trigger date) | Other targets
Assessment ​ | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Initial needs assessment | 3 days |  | Assessment ​ | Initial needs assessments completed within 72 hours​ of the event. | Initial needs assessment | 3 days |  | Planning​ & resource Mobilisation | Approval of decision for DREF operation escalation to EA | Escalation from DREF to EA apporval | 0 days (disaster trigger date) |  | Assessment ​ | Needs assessments of triggers to identify the need for an EA. | Initial needs assessment | 3 days
Planning​ & resource Mobilisation | Approval of decision for DREF operation escalation to EA | Escalation from DREF to EA apporval | 0 days (disaster trigger date) |  | Risk and accountability | Risk management one pager using country risk the dashboard developed within 48h after the approval | Risk management one pager | 12 days |  | Planning​ & resource Mobilisation | Disaster Brief done for the Management Call to inform the FAD between 48-72 h | Disaster Brief | 2-3 days |  | Planning​ & resource Mobilisation | Approval of decision for DREF operation escalation to EA | Escalation from DREF to EA apporval | 0 days (disaster trigger date)
Planning​ & resource Mobilisation | Disaster Brief done to inform the FAD between 48-72 h | Disaster Brief | 2-3 days |  |  | Project manager and appeal manager responsibilities one pager is shared with approval (max 14 days after trigger) | Project and appeal manager responsibilities one pager | 14 days |  | Planning​ & resource Mobilisation | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | EA launch date | 4 days |  | Planning​ & resource Mobilisation | Disaster Brief done for the Management Call to inform the FAD between 48-72 | Disaster Brief | 2-3 days
Planning​ & resource Mobilisation | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | EA launch date | 4 days |  | Planning​ & resource Mobilisation | DREF approved within 10 days of the trigger. 14 if the NS has started responding. | DREF approved | 10 days |  | Planning​ & resource Mobilisation | Operational Strategy validated 12 days after the EA | Operational Strategy validated | 11 days |  | Planning​ & resource Mobilisation | EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | EA launch date | 4 days
Planning​ & resource Mobilisation | Operational Strategy validated 7 days after the EA | Operational Strategy validated | 11 days |  |  | Approval by the DREF appeal manager within 24h of receiving the final package | Approval by the DREF appeal manager | 14 days |  | Planning​ & resource Mobilisation | % coverage of the EA | coverage of the EA | - | No target | Planning​ & resource Mobilisation | Operational Strategy validated 10 to 14 days after the EA | Operational Strategy validated | 11 days
Planning​ & resource Mobilisation | % coverage of the EA | coverage of the EA | - | No target | Surge (If/when relevant) | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster (if relevant) | Green light from receiving NS | 1 day |  | Planning​ & resource Mobilisation | A resource mobilization plan is developed and approved within 2 weeks of the EA | Resource mobilization plan | 18 days |  | Planning​ & resource Mobilisation | % coverage of the EA | coverage of the EA | - | No target
Planning​ & resource Mobilisation | A resource mobilization plan is developed and approved within 2 weeks of the EA | Resource mobilization plan | 18 days |  |  | RR personnel Alert sent within 12h of the request | RR personnel Alert sent | 2 days |  | Surge | Regional RR personnel Alert sent within 12h of the request | RR personnel Alert sent | 1 day |  | Planning​ & resource Mobilisation | A resource mobilization plan is developed and approved within 3 to 4 weeks of the EA that looks at long term funding and sustianability. | Resource mobilization plan | 18 days
Surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Green light from receiving NS | 1 day |  |  | Identification of 1st RR personnel within 48h of the 1st alert | Identification of 1st RRP | 3 days |  | Surge | Identification of 1st RR personnel within 48h of the 1st alert | RR personnel Alert sent | 2 days |  | Surge | IFRC advocates with NS for the approval and use of Surge or in country capacity from movment partners within the first 5 days of the trigger | IFRC coordination with NS or movement partners on surge | 7 days
Surge | RR personnel Alert sent within 12h of the request | RR personnel Alert sent | 2 days |  |  | % of female and male out of the RRP deployed | Female share in deployoment | - | No target | Surge | % of female and male out of the RRP deployed | Female share in deployoment | - | No target | Surge | RR personnel Alert sent within 12h of the request | RR personnel Alert sent | 2 days
Surge | Identification of 1st RR personnel within 48h of the 1st alert | Identification of 1st RRP | 3 days |  |  | % of RRP coming within the region of the disaster | Regional RRP share in deployment | - | No target | Surge | % of RRP coming within the region of the disaster | Regional RRP share in deployment | - | No target | Surge | Identification of 1st rotation RR personnel within 5 days of the alert *if not aligned to readiness process could be slower | Identification of 1st RRP | 3 days
Surge | % of female and male out of the RRP deployed | Female share in deployoment | - | No target |  | % of RR deployed arriving in country of operation within 4 days from deployment message | RRP share ariving in country within 4 days of message | - | <50% Bad > 50% Okay >75% good | Surge | % of RR deployed arriving in country within 4 days from deployment message | RRP share ariving in country within 4 days of message | - | <50% Bad > 50% Okay >75% good | Surge | % of female and male out of the RRP deployed | Female share in deployoment | - | No target
Surge | % of RRP coming within the region of the disaster | Regional RRP share in deployment | - | No target | Procurement and Logistics | Supply chain plan developed within 1 week of DREF approval | Supply chain plan | 19 days |  | HR Planning and Recruitment | Key initial longer-term positions (for the Regional/multi country level) identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Key initial longer-term positions identified and requested via HR system | 11 days |  | Surge | % of RRPs with 3 months deployments | RRPs with 3 months deployment | -
Surge | % of RR deployed arriving in country of operation within 4 days from deployment message | RRP share ariving in country within 4 days of message | - | <50% Bad > 50% Okay >75% good |  | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | NFI (or emergency items) being delivered | 2 |  | HR Planning and Recruitment | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | HR advertises key intial longer term position | 13 days |  | Surge | % of RRP coming within the region of the disaster | Regional RRP share in deployment | - | No target
HR Planning and Recruitment | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Key initial longer-term positions identified and requested via HR system | 11 days |  | Financial management | Project funding agreements (PFAs) signed by the NS and the IFRC no longer than 7 days from the DREF approval | Project Funding Agreements (PFA) signed | 17 days |  | Coordination | Establish a Multi country coordination mechanimsms with the membership for the crisis | Multi country coordination mechanism | 1 day |  | Surge | % of RR deployed arriving in country of operation within 4 days from deployment message | RRP share ariving in country within 4 days of message | - | <50% Bad > 50% Okay >75% good
HR Planning and Recruitment | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | HR advertises key intial longer term position | 13 days |  |  | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF approval | Process the Request for Payment to be sent to Treasury | 21 days |  | Procurement and Logistics | Supply chain plan developed for the regional needs between logs and ops within 1 week of the approved EA | Supply chain plan | 11 days |  | HR Planning and Recruitment | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | Key initial longer-term positions identified and requested via HR system | 11 days
Coordination | Hold a Mini Summit within 48 h of the disaster | Mini summit | 2 days |  |  | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Bank transfer process | 22 days |  | Procurement and Logistics | Fully approved and submitted multi country requisitions for NFIs within 1 week of the EA (when relevant) | Requisitions for NFIs fully approved and submitted | 11 days |  | HR Planning and Recruitment | Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | HR advertises key intial longer term position | 13 days
Coordination | The Movement Joint statement is produced 48h after the Mini Summit | Movement Joint statement | 4 days |  |  | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Confirmation from the NSs of the funds received | 30 days |  | Procurement and Logistics | NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | NFI (or emergency items) being delivered | 14 days |  | Coordination | Hold a Mini Summit within 48 h of the disaster | Mini summit | 2 days
Coordination | review/adapt membership coordination for the context for this specific emergency | Membership coordination review/ adaption | 7 days |  | Programme delivery | First round of payment received to the target beneficiaries four weeks after the DREF approval | First round of payment received to the target beneficiaries | 30 days |  | Information Management | A multi country dashboard is in place and updated timely to display the situation and the activities being implemented | Multi country dashboard | 1 day |  | Coordination | The Movement Joint statement is produced 48h after the Mini Summit | Movement Joint statement | 4 days
Coordination | Appropriate membership coordination is in place after 24h of disaster | Membership coordination in place | 1 day |  |  | % of targeted population receiving assistance | NFIs distributed to targetted population | - |  | Financial management | A breakdown of the Financial allocation per country is made within 5 days of the approval of the EA | Breakdown of financial allocation | 9 days |  | Coordination | review/adapt membership coordination for the context for this specific emergency | Membership coordination review/ adaption | 7 days
Procurement and Logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Supply chain plan | 11 days |  |  | EHI distributed to targetted population on time | Targeted population receiving assistance | - |  | Financial management | Transferts to NS & IFRC Sec. Structure are made within 5 days of the allocation table | Transferts to NS & IFRC Sec. Structure | 14 days |  | Coordination | Appropriate membership coordination is in place after 24h of disaster | Membership coordination in place | 1 day
Procurement and Logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Requisitions for NFIs fully approved and submitted | 11 days |  |  | Implementation rate: 30% after month 1 | implementation rate of available budget | - |  | Programme delivery | Cumulated % of targeted population receiving assistance | Share of targeted population receiving assistance | - |  | Procurement and Logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | Supply chain plan | 11 days
Procurement and Logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | NFI (or emergency items) being delivered | 14 days |  | Security | Operation is MSR (v.2021) compliant | MSR compliant | 7 days |  | Programme delivery | Cumulated % implementation rate of available budget | Share of implementation rate | - |  | Procurement and Logistics | Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | Requisitions for NFIs fully approved and submitted | 11 days
Information Management | A dashboard is in place and updated timely to display the situation and the activities being implemented | Dashboard in place | 1 day |  |  | If the country is not MSR, enough resource (HR/ Funds) have been allocated to operate in a Red/ orange security phase areas | If not MSR compliant, enough recources allocated | 7 days | [6 empty] | Procurement and Logistics | NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | NFI (or emergency items) being delivered | 14 days
Financial management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Project Funding Agreements (PFA) signed | 11 days | [11 empty] | Information Management | A dashboard is in place and updated timely to display the situation and the activities being implemented | Dashboard in place | 1 day
Financial management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Process the Request for Payment to be sent to Treasury | 14 days | [11 empty] | Financial management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | Project Funding Agreements (PFA) signed | 11 days
Financial management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Bank transfer process | 16 days | [11 empty] | Financial management | After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | Process the Request for Payment to be sent to Treasury | 14 days
Financial management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Confirmation from the NSs of the funds received | 20 days | [11 empty] | Financial management | Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | Bank transfer process | 16 days
Programme delivery | First round of payment received to the target beneficiaries four weeks after the EA launch for sudden onset (when relevant and when CVA is planned) | First round of payment received to the target beneficiaries | 32 days | [11 empty] | Financial management | Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Confirmation from the NSs of the funds received | 20 days
Programme delivery | NFIs distributed to targetted population within one month of the disaster | NFIs distributed to targetted population | 28 days | [11 empty] | Programme delivery | First round of payment received to the target beneficiaries four weeks after the EA launch for sudden onset (when relevant and when CVA is planned) | First round of payment received to the target beneficiaries | 32 days
Programme delivery | % of targeted population receiving assistance | targeted population receiving assistance | - | No target | [10 empty] | Programme delivery | NFIs distributed to targetted population within one month of the disaster | NFIs distributed to targetted population | 28 days
Programme delivery | % implementation rate of available budget | implementation rate of available budget | - | No target | [10 empty] | Programme delivery | % of targeted population receiving assistance | targeted population receiving assistance | - | No target
Security | Operation is MSR (v.2021) compliant | MSR compliant | 7 days | [11 empty] | Programme delivery | % implementation rate of available budget | implementation rate of available budget | - | No target
Security | If the country is not MSR, enough resource (HR/Funds) have been allocated to operate in a Red/orange security phase areas | If not MSR compliant, enough recources allocated | 7 days | [11 empty] | Security | Operation is MSR (v.2021) compliant | MSR compliant | 7 days
[15 empty] | Security | If the country is not MSR, enough resource (HR/Funds) have been allocated to operate in a Red/orange security phase areas | If not MSR compliant, enough recources allocated | 7 days