## EA Funded Operations
EA funded operations - COUNTRY INDICATORS | Disaster trigger date: |  | 2024-08-09 | FAD approved:
| EA launch date: |  | 2024-08-12 | Appeal code |  |  |  |  | Timeline starts from the day of disaster trigger date (for sudden onset crises)
[9 empty] | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-16 | 2024-08-19 | 2024-08-23 | 2024-08-30 | 2024-09-09 | 2024-10-09 | 2024-11-09
Area | Indicator | Start date (dd.mm.yyyy) | Expected date of completion (dd.mm.yyyy) | Actual date of completion (dd.mm.yyyy) | Responsible | Accountable | Supporting | 12 h | 24 h | 48 h | 72 h | 96 h | 1 week | 10 days | 2 weeks | 3 weeks | 1 month | 2 months | 3 months | Proposed Actions | Comments by those 'Responsible' | Comments by those 'Accountable' | Other comments
Assessment ​ | Initial needs assessments completed and disseminated within 72 hours​ of the event. | Disaster trigger date |  |  | HoD or HEOPs | HoD | Regional HoHDCC |  | 2024-08-12: Achieved
Planning​ & resource Mobilisation | Disaster Brief done to inform the FAD between 48-72 h | Disaster trigger date |  |  | Head of IM, Quality & DREF | Head of IM, Quality & DREF | DCC Team |  | 2024-08-11: Achieved; 2024-08-12: Not achieved
| EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). | FAD approved date |  |  | HOD | Regional Director & DCC Director | Director of DCC |  | 2024-08-13: *Expected to be achieved*
| Operational Strategy validated 7 days after the EA | EA launch date |  |  | Ops coordinator Manager | Director of DCC | Regional HoHDCC/ Deputy RD |  | 2024-08-19: *Expected to be achieved*; 2024-08-23: *Expected to be achieved*
| % coverage of the EA | EA launch date |  |  | SPRM RO | SPRM Gva |  |  | 2024-08-19: *% to be noted here*; 2024-08-23: *% to be noted here*; 2024-08-30: *% to be noted here*; 2024-09-09: *% to be noted here*; 2024-10-09: *% to be noted here*; 2024-11-09: *% to be noted here*
| A resource mobilization plan is developed and approved within 2 weeks of the EA | EA launch date |  |  | Regional SPRM | RD | SPRM GVA |  | 2024-08-23: *Expected to be achieved*; 2024-08-30: *Expected to be achieved*
Surge | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster | Disaster trigger date |  |  | HoD | HoD | RD |  | 2024-08-10: *Expected to be achieved*
| RR personnel Alert sent within 12h of the request | Request date |  |  | SURGE GVA | OPs Co Manager GVA | RD |  | 2024-08-11: *Expected to be achieved*
| Identification of 1st RR personnel within 48h of the 1st alert | Alert sending date |  |  | SURGE GVA | Ops Manager GVA | Regional HoHDCC |  | 2024-08-12: *Expected to be achieved*; 2024-08-13: *Expected to be achieved*
| % of female and male out of the RRP deployed |  |  |  | SURGE GVA | Ops Manager GVA |  |  | 2024-08-23: *% female out of total*; 2024-09-09: *% female out of total*; 2024-10-09: *% female out of total*; 2024-11-09: *% female out of total*
| % of RRP coming within the region of the disaster |  |  |  | SURGE GVA | Regional HoHDCC | Deputy Regional HoHDCC |  | 2024-08-23: *% from region out of total*; 2024-09-09: *% from region out of total*; 2024-10-09: *% from region out of total*; 2024-11-09: *% from region out of total*
| % of RR deployed arriving in country of operation within 4 days from deployment message | Deployment message date |  |  | SURGE GVA | Ops Manager GVA | Regional HoHDCC |  | 2024-08-16: *%of RR*; 2024-08-23: *% of RR*; 2024-09-09: *% of RR*; 2024-10-09: *% of RR*; 2024-11-09: *% of RR*
HR Planning and Recruitment | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication | EA launch date |  |  | Ops Leadership Country | HoD | Deputy RD |  | 2024-08-19: *Expected to be achieved*; 2024-08-23: *Expected to be achieved*
| Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Approval date |  |  | HR RO | HR Gva | Deputy RD |  | 2024-08-23: *Expected to be achieved*
Coordination | Hold a Mini Summit within 48 h of the disaster | Disaster trigger date |  |  | HoD | RD | GVA SMCC |  | 2024-08-11: *Expected to be achieved*
| The Movement Joint statement is produced 48h after the Mini Summit |  |  |  | HoD | RD | GVA SMCC |  | 2024-08-13: *Expected to be achieved*
| review/adapt membership coordination for the context for this specific emergency |  |  |  | HoD | HoD | bar: 2024-08-11
| Appropriate membership coordination is in place after 24h of disaster | Disaster trigger date |  |  | HoD | HoD | OMMC/ HDCC | *Expected to be achieved* | 2024-08-10: *Expected to be achieved*
Procurement and Logistics | Supply chain plan developed between logs and ops coordinator within 1 week of the approved EA | EA launch date |  |  | Ops & Logs Leadership in country | HoHDCC/ Logs Region | DCC & Logs Director |  | 2024-08-19: *Expected to be achieved*; 2024-08-23: *Expected to be achieved*
| Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) | EA launch date |  |  | Ops Leadership Country | HOD | HDCC RO |  | 2024-08-19: *Expected to be achieved*; 2024-08-23: *Expected to be achieved*
| NFI (or emergencies items) being delivered to the country in 3 days since the approval of the Requistion | EA launch date |  |  | Logistics RO | Logistics Gva | Logistics Gva |  | 2024-08-23: *Expected to be achieved*; 2024-08-30: *Expected to be achieved*
Information Management | A dashboard is in place and updated timely to display the situation and the activities being implemented | EA launch date |  |  | IM Lead Country | IM Lead Gva | IM RO |  | 2024-08-10: *Expected to be achieved*; 2024-08-12: *Expected to be achieved*; 2024-08-16: *Expected to be achieved*; 2024-08-23: *Expected to be achieved*; 2024-09-09: *Expected to be achieved*
Financial management | Project Funding Agreements (PFA) signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval | EA launch date |  |  | HoD | HoD | RD |  | 2024-08-19: *Expected to be achieved*
| After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval | EA launch date |  |  | Ops Leadership Country | HOD | Finance RO |  | 2024-08-23: *Expected to be achieved*
| Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | RFP receival/approval date |  |  | Finance RO | Finance Gva | HOD |  | 2024-08-23: *Expected to be achieved*; 2024-08-30: *Expected to be achieved*
| Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | value date of the transfer |  |  | HoD | HoD | Finance Country |  | 2024-08-30: *Expected to be achieved*
Programme delivery | First round of payment received to the target beneficiaries four weeks after the EA launch for sudden onset (when relevant and when CVA is planned) | EA launch date |  |  | Project Manager Country | HoD | Sector lead(s) |  | 2024-09-09: *Expected to be achieved*
| NFIs distributed to targetted population within one month of the disaster | Disaster trigger date |  |  | Project Manager Country | HoD | Sector lead(s) / Logistics RO |  | 2024-09-09: *Expected to be achieved*; 2024-10-09: *% to be noted here*; 2024-11-09: *% to be noted here*
| % of targeted population receiving assistance | EA launch date |  |  | Ops leadership in country | HoD | Sector lead(s) |  | 2024-08-23: *% to be noted here*; 2024-09-09: *% to be noted here*; 2024-10-09: *% to be noted here*; 2024-11-09: *% to be noted here*
| % implementation rate of available budget | EA launch date |  |  | Ops leadership in country | HOD | Sector lead(s) |  | 2024-08-23: *% to be noted here*; 2024-08-30: *% to be noted here*; 2024-09-09: *% to be noted here*; 2024-10-09: *% to be noted here*; 2024-11-09: *% to be noted here*
Security | Operation is MSR (v.2021) compliant | EA launch date |  |  | HOD | RD | Security team (Country/ Region/ Geneva) |  | 2024-08-16: *Expected to be achieved*
| If the country is not MSR, enough resource (HR/Funds) have been allocated to operate in a Red/orange security phase areas | EA launch date |  |  | HOD | RD | Security team (Country/ Region/ Geneva) |  | 2024-08-16: *Expected to be achieved*
To report under (color) | To report as
Done or not done (timeliness indicators)
To fill data - % or # or other (as applicable)
1° Note to the person "responsible" , please write in the appropriate column if the task is achieved or not. It is expected that the task is achieved at the "blue" case but feel free to include it in the right column when done.
For the yellow case, please write the % or # in the yellow cases.
2° Please note that these indicators are standardized, consequently they may not apply in specific context. If that the case, feel free to mention "NA" in the Column "E"

## DREF Funded Operations
DREF funded operations | Disaster trigger date: |  | 2024-08-09 | FAD approved: |  |  |  |  | Timeline starts from the day of disaster trigger date (for sudden onset crises)
| DREF launch date: |  | 2024-08-12 | Appeal code
[9 empty] | 2024-08-10 | 2024-08-11 | 2024-08-12 |  | 2024-08-16 | 2024-08-19 | 2024-08-23 | 2024-08-30 | 2024-09-09 | 2024-10-09 | 2024-11-09
Area | Indicator | Start date (dd.mm.yyyy) | Expected date of completion (dd.mm.yyyy) | Actual date of completion (dd.mm.yyyy) | Responsible | Accountable | Supporting | 12 h | 24 h | 48 h | 72 h | 96 h | 1 week | 10 days | 2 weeks | 3 weeks | 1 month | 2 months | 3 months | Comments | Proposed Actions
Assessment ​ | Initial needs assessments completed within 72 hours​ of the event. | Disaster trigger date |  |  | Ops Leadership in country | HoD | Regional HoHDCC |  |  |  | *Expected to be achieved*
Risk and accountability | Risk management one pager using country risk the dashboard developed within 48h after the approval | DREF approval date |  |  | DREF Accountability SO | DREF Lead |  |  |  | *Expected to be achieved*
| Project manager and appeal manager responsibilities one pager is shared with approval (max 14 days after trigger) | Disaster trigger date |  |  | DREF SO | DREF Lead | DREF Appeal Manager | [6 empty] | *Expected to be achieved* | *Expected to be achieved*
Planning​ & resource Mobilisation | DREF approved within 10 days of the trigger. 14 if the NS has started responding. | Disaster trigger date |  |  | DREF Lead | DREF Appeal manager | USG NSDOC | [6 empty] | *Expected to be achieved* | *Expected to be achieved*
| Approval by the DREF appeal manager within 24h of receiving the final package | Final package recieval date |  |  | DREF Appeal manager | DREF Appeal manager | USG NSDOC and DREF Lead | [6 empty] | *Expected to be achieved* | *Expected to be achieved*
Surge (If/when relevant) | IFRC having the green light from the receiving NS to deploy RR 24h after the disaster (if relevant) | Disaster trigger date |  |  | HoD | HoD | RD |  | *Expected to be achieved*
| RR personnel Alert sent within 12h of the request | Request date |  |  | SURGE GVA | HoD | RD |  |  | *Expected to be achieved*
| Identification of 1st RR personnel within 48h of the 1st alert | Alert sending date |  |  | SURGE GVA | Ops Manager GVA | Regional HoHDCC |  |  | *Expected to be achieved*
| % of female and male out of the RRP deployed |  |  |  | SURGE GVA | Ops Manager GVA | Deputy RD | [7 empty] | *% female out of total* |  | *% female out of total* | *% female out of total* | *% female out of total*
| % of RRP coming within the region of the disaster |  |  |  | SURGE GVA | Regional HoHDCC | Deputy Regional HoHDCC | [7 empty] | *% from region out of total* |  | *% from region out of total* | *% from region out of total* | *% from region out of total*
| % of RR deployed arriving in country of operation within 4 days from deployment message | Deployment message date |  |  | SURGE GVA | Ops Manager GVA | Regional HoHDCC | [5 empty] | *%of RR* |  | *% of RR* |  | *% of RR* | *% of RR* | *% of RR*
Procurement and Logistics | Supply chain plan developed within 1 week of DREF approval | DREF approval date |  |  | Ops & Logs Leadership in country | HoHDCC/ Logs Region | DCC & Logs Director | [7 empty] | *Expected to be achieved*
| NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | Requisition date |  |  | Logistics RO | Logistics Gva | Logistics Gva | [7 empty] | *Expected to be achieved*
Financial management | Project funding agreements (PFAs) signed by the NS and the IFRC no longer than 7 days from the DREF approval | DREF approval date |  |  | HoD | HoD | RD | [7 empty] | *Expected to be achieved*
| After PFA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF approval | DREF approval date |  |  | Ops Leadership Country | HOD | Finance RO | [7 empty] | *Expected to be achieved* | *Expected to be achieved*
| Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved | RoP recieval date |  |  | Finance RO | Finance Gva | HOD | [8 empty] | *Expected to be achieved* | *Expected to be achieved*
| Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer | Value date of transfer |  |  | HoD | HoD | Finance Country | [9 empty] | *Expected to be achieved*
Programme delivery | First round of payment received to the target beneficiaries four weeks after the DREF approval | DREF approval date |  |  | Project Manager Country | HoD | Sector lead(s) | [9 empty] | *Expected to be achieved* | *% to be noted here* | *% to be noted here*
| % of targeted population receiving assistance | DREF approval date |  |  | Ops leadership in country | HoD | Sector lead(s) | [7 empty] | *% to be noted here* |  | *% to be noted here* | *% to be noted here* | *% to be noted here*
| EHI distributed to targetted population on time | Disaster trigger date |  |  | Project Manager Country | HoD | Sector lead(s) / Logistics RO | [9 empty] | *% to be noted here* | *% to be noted here* | *% to be noted here*
| Implementation rate: 30% after month 1 | DREF approval date |  |  | Ops leadership in country | HOD | Sector lead(s) | [9 empty] | *% to be noted here* | *% to be noted here* | *% to be noted here*
Security | Operation is MSR (v.2021) compliant | DREF approval date |  |  | HOD | RD | Security team (Country/ Region/ Geneva) | [5 empty] | *Expected to be achieved*
| If the country is not MSR, enough resource (HR/ Funds) have been allocated to operate in a Red/ orange security phase areas | DREF approval date |  |  | HOD | RD | Security team (Country/ Region/ Geneva) | [5 empty] | *Expected to be achieved*
To report under (color) | To report as
Done or not done (timeliness indicators)
To fill data - % or # or other (as applicable)
1° Note to the person "responsible" , please write in the appropriate column if the task is achieved or not. It is expected that the task is achieved at the "blue" case but feel free to include it in the right column when done.
For the yellow case, please write the % or # in the yellow cases.
2° Please note that these indicators are standardized, consequently they may not apply in specific context. If that the case, feel free to mention "NA" in the Column "E"

## Region Multi Country Indicators
EA funded operations - REGIONAL INDICATORS | Disaster trigger date: |  | 2024-10-29 | FAD approved:
| EA launch date: |  | 2024-08-20 | Appeal code |  |  |  |  | Timeline starts from the day of disaster trigger date (for sudden onset crises)
[9 empty] | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-05 | 2024-11-08 | 2024-11-12 | 2024-11-19 | 2024-11-29 | 2024-12-29 | 2025-01-29
Area | Indicator | Start date (dd.mm.yyyy) | Expected date of completion (dd.mm.yyyy) | Actual date of completion (dd.mm.yyyy) | Responsible | Accountable | Supporting | 12 h | 24 h | 48 h | 72 h | 96 h | 1 week | 10 days | 2 weeks | 3 weeks | 1 month | 2 months | 3 months | Comments | Proposed Actions
Planning​ & resource Mobilisation | Disaster Brief done for the Management Call to inform the FAD between 48-72 h | EA launch date |  |  | Head of IM, Quality & DREF | Head of IM, Quality & DREF | DCC Team |  | 2024-10-31: *Expected to be achieved*; 2024-11-01: *Expected to be achieved*
| EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). |  |  |  | Heads of HDCC involved | Regional Director & DCC Director | Director of DCC |  | 2024-11-02: *Expected to be achieved*
| Operational Strategy validated 12 days after the EA |  |  |  | Ops coordinator Manager | Director of DCC | Regional HoHDCC/ Deputy RD |  | 2024-11-12: *Expected to be achieved*
| % coverage of the EA |  |  |  | SPRM RO | SPRM Gva |  |  | 2024-11-08: *% to be noted here*; 2024-11-12: *% to be noted here*; 2024-11-19: *% to be noted here*; 2024-11-29: *% to be noted here*; 2024-12-29: *% to be noted here*; 2025-01-29: *% to be noted here*
| A resource mobilization plan is developed and approved within 2 weeks of the EA | EA launch date |  |  | Regional SPRM | RD | SPRM GVA |  | 2024-11-12: *Expected to be achieved*; 2024-11-19: *Expected to be achieved*
Surge | Regional RR personnel Alert sent within 12h of the request | Disaster trigger date |  |  | SURGE GVA | OPs Co Manager GVA | RD |  | 2024-10-30: *Expected to be achieved*
| Identification of 1st RR personnel within 48h of the 1st alert | Alert sending date |  |  | SURGE GVA | Ops Manager GVA | Regional HoHDCC |  | 2024-11-01: *Expected to be achieved*; 2024-11-02: *Expected to be achieved*
| % of female and male out of the RRP deployed |  |  |  | SURGE GVA | Ops Manager GVA |  |  | 2024-11-12: *% female out of total*; 2024-11-29: *% female out of total*; 2024-12-29: *% female out of total*; 2025-01-29: *% female out of total*
| % of RRP coming within the region of the disaster |  |  |  | SURGE GVA | Regional HoHDCC | Deputy Regional HoHDCC |  | 2024-11-12: *% from region out of total*; 2024-11-29: *% from region out of total*; 2024-12-29: *% from region out of total*; 2025-01-29: *% from region out of total*
| % of RR deployed arriving in country within 4 days from deployment message | Deployment message date |  |  | SURGE GVA | Ops Manager GVA | Regional HoHDCC |  | 2024-11-05: *%of RR*; 2024-11-12: *% of RR*; 2024-11-29: *% of RR*; 2024-12-29: *% of RR*; 2025-01-29: *% of RR*
HR Planning and Recruitment | Key initial longer-term positions (for the Regional/multi country level) identified by operational leadership and requested via submission in the HR system, one week after the EA publication | EA launch date |  |  | HDCC Head | HoD | Deputy RD |  | 2024-11-08: *Expected to be achieved*; 2024-11-12: *Expected to be achieved*
| Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. | Approval date |  |  | HR RO | HR Gva | Deputy RD |  | 2024-11-12: *Expected to be achieved*
Coordination | Establish a Multi country coordination mechanimsms with the membership for the crisis | Disaster trigger date |  |  | DRD | RD | GVA SMCC | *Expected to be achieved* | 2024-10-30: *Expected to be achieved*
Procurement and Logistics | Supply chain plan developed for the regional needs between logs and ops within 1 week of the approved EA | EA launch date |  |  | HDCC & Logs RO | DRD | DCC & Logs Director |  | 2024-11-08: *Expected to be achieved*; 2024-11-12: *Expected to be achieved*
| Fully approved and submitted multi country requisitions for NFIs within 1 week of the EA (when relevant) | EA launch date |  |  | HDCC & Logs RO | DRD | HDCC RO |  | 2024-11-08: *Expected to be achieved*; 2024-11-12: *Expected to be achieved*
| NFI (or emergencies items) being delivered to the country in 3 days since the Requistion | EA launch date |  |  | Logistics RO | Logistics Gva | Logistics Gva |  | 2024-11-12: *Expected to be achieved*; 2024-11-19: *Expected to be achieved*
Information Management | A multi country dashboard is in place and updated timely to display the situation and the activities being implemented | EA launch date |  |  | IM RO | IM Lead Gva | IM RO |  | 2024-10-30: *Expected to be achieved*; 2024-11-01: *Expected to be achieved*; 2024-11-05: *Expected to be achieved*; 2024-11-12: *Expected to be achieved*; 2024-11-29: *Expected to be achieved*
Financial management | A breakdown of the Financial allocation per country is made within 5 days of the approval of the EA | EA launch date |  |  | Head of HDCC | DRD & RD | Finance RO |  | 2024-11-08: *Expected to be achieved*
| Transferts to NS & IFRC Sec. Structure are made within 5 days of the allocation table | EA launch date |  |  | Finance RO | Finance Gva | DRD |  | 2024-11-12: *Expected to be achieved*
Programme delivery | Cumulated % of targeted population receiving assistance | EA launch date |  |  | Head of HDCC | DRD | Sector lead(s) |  | 2024-11-12: *% to be noted here*; 2024-11-29: *% to be noted here*; 2024-12-29: *% to be noted here*; 2025-01-29: *% to be noted here*
| Cumulated % implementation rate of available budget | Disaster trigger date |  |  | Head of HDCC | DRD | Sector lead(s) |  | 2024-11-12: *% to be noted here*; 2024-11-19: *% to be noted here*; 2024-11-29: *% to be noted here*; 2024-12-29: *% to be noted here*; 2025-01-29: *% to be noted here*
To report under (color) | To report as
Done or not done (timeliness indicators)
To fill data - % or # or other (as applicable)
1° Note to the person "responsible" , please write in the appropriate column if the task is achieved or not. It is expected that the task is achieved at the "blue" case but feel free to include it in the right column when done.
For the yellow case, please write the % or # in the yellow cases.
2° Please note that these indicators are standardized, consequently they may not apply in specific context. If that the case, feel free to mention "NA" in the Column "E"

## Protracted Crises
COUNTRY INDICATORS | Disaster trigger date: | 2024-08-09 | FAD approved: | [5 empty] | Maybe needs to be annual but also quarterly process?
| EA launch date: | 2024-08-12 | Appeal code | [5 empty] | Timeline starts from the day of escalation/ trigger data leading to EA launch ( for slow onset crises)
[9 empty] | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-16 | 2024-08-19 | 2024-08-23 | 2024-08-30 | 2024-09-09 | 2024-10-09 | 2024-11-09
Area | Indicator | Expected date of completion (dd.mm.yyyy) | Actual date of completion (dd.mm.yyyy) | Responsible | Accountable | Supporting | Before | 12 h | 24 h | 48 h | 72 h | 96 h | 1 week | 10 days | 2 weeks | 3 weeks | 1 month | 2 months | 3 months | Proposed Actions | Comments by those 'Responsible' | Comments by those 'Accountable' | Other comments
Assessment ​ | Needs assessments of triggers to identify the need for an EA. |  |  | Ops lead. | HoD | Regional HoHDCC | Achieved | bar: 2024-08-12
Planning​ & resource Mobilisation | Disaster Brief done for the Management Call to inform the FAD between 48-72 |  |  | Head of IM, Quality & DREF | Head of IM, Quality & DREF | DCC Team |  |  | 2024-08-11: Achieved; 2024-08-12: Achieved
| EA is launched within 24 hours after the FAD has been approved (or within 48 hours after field report was published). |  |  | HoD | Regional Director & DCC Director | Director of DCC |  |  | 2024-08-13: *Expected to be achieved*
| Operational Strategy validated 10 to 14 days after the EA |  |  | Ops coordinator Manager | Director of DCC | Regional HoHDCC/ Deputy RD |  |  | 2024-08-19: *Expected to be achieved*; 2024-08-23: *Expected to be achieved*
| % coverage of the EA |  |  | SPRM RO | SPRM Gva |  |  |  | 2024-08-19: *% to be noted here*; 2024-08-23: *% to be noted here*; 2024-08-30: *% to be noted here*; 2024-09-09: *% to be noted here*; 2024-10-09: *% to be noted here*; 2024-11-09: *% to be noted here*
| A resource mobilization plan is developed and approved within 3 to 4 weeks of the EA that looks at long term funding and sustianability. |  |  | Regional SPRM | RD | SPRM GVA |  |  | 2024-08-30: *Expected to be achieved*; 2024-09-09: *Expected to be achieved*
Surge | IFRC advocates with NS for the approval and use of Surge or in country capacity from movment partners within the first 5 days of the trigger |  |  | HoD | HoD | RD |  |  | 2024-08-16: *Expected to be achieved*
| RR personnel Alert sent within 12h of the request |  |  | SURGE GVA | OPs Co Manager GVA | RD |  |  | 2024-08-11: *Expected to be achieved*
| Identification of 1st rotation RR personnel within 5 days of the alert *if not aligned to readiness process could be slower |  |  | SURGE GVA | Ops Manager GVA | Regional HoHDCC |  |  | 2024-08-12: *Expected to be achieved*; 2024-08-13: *Expected to be achieved*
| % of female and male out of the RRP deployed |  |  | SURGE GVA | Ops Manager GVA |  |  |  | 2024-08-23: *% female out of total*; 2024-09-09: *% female out of total*; 2024-10-09: *% female out of total*; 2024-11-09: *% female out of total*
| duration - % of 3 months deployments |  |  | SURGE GVA | Ops Manager GVA | bar: 2024-08-23; 2024-09-09 to 2024-11-09
| % of RRP coming within the region of the disaster |  |  | SURGE GVA | Regional HoHDCC | Deputy Regional HoHDCC |  |  | 2024-08-23: *% from region out of total*; 2024-09-09: *% from region out of total*; 2024-10-09: *% from region out of total*; 2024-11-09: *% from region out of total*
| % of RR deployed arriving in country of operation within 4 days from deployment message |  |  | SURGE GVA | Ops Manager GVA | Regional HoHDCC |  |  | 2024-08-16: *%of RR*; 2024-08-23: *% of RR*; 2024-09-09: *% of RR*; 2024-10-09: *% of RR*; 2024-11-09: *% of RR*
HR Planning and Recruitment | Key initial longer-term positions identified by operational leadership and requested via submission in the HR system, one week after the EA publication |  |  | Ops Leadership Country | HoD | Deputy RD |  |  | 2024-08-19: *Expected to be achieved*; 2024-08-23: *Expected to be achieved*
| Once approved in the HR system and pre-classified JD provided, HR advertises key initial longer-term positions within 48 hours. |  |  | HR RO | HR Gva | Deputy RD |  |  | 2024-08-23: *Expected to be achieved*
Coordination | Hold a mini summit within 48 h of the disaster |  |  | HoD | RD | GVA SMCC |  |  | 2024-08-11: *Expected to be achieved*
| The Movement Joint statement is produced 48h after the Mini Summit |  |  | HoD | RD | GVA SMCC |  |  | 2024-08-11: *Expected to be achieved*
| Review/adapt membership coordination framework for the conext for this specific emergency |  |  | HoD | HoD |  |  |  | 2024-08-11: *Expected to be achieved*
| Ensure an appropriate membership coordination framework is in place after 24h of trigger |  |  | HoD | HoD | OMMC/ HDCC |  | *Expected to be achieved* | 2024-08-10: *Expected to be achieved*
Procurement and Logistics | Initial supply chain plan developed between logs and ops coordinator within 1 week of the approved EA |  |  | Ops & Logs Leadership in country | HoHDCC/ Logs Region | DCC & Logs Director |  |  | 2024-08-19: *Expected to be achieved*; 2024-08-23: *Expected to be achieved*
| Fully approved and submitted requisitions for NFIs within 1 week of the EA (when relevant) |  |  | Ops Leadership Country | HOD | HDCC RO |  |  | 2024-08-19: *Expected to be achieved*; 2024-08-23: *Expected to be achieved*
| NFI (or emergencies items) being delivered to the country in 3 days since the Requistion |  |  | Logistics RO | Logistics Gva | Logistics Gva |  |  | 2024-08-23: *Expected to be achieved*; 2024-08-30: *Expected to be achieved*
Information Management | A dashboard is in place and updated timely to display the situation and the activities being implemented |  |  | IM Lead Country | IM Lead Gva | IM RO |  |  | 2024-08-10: *Expected to be achieved*; 2024-08-12: *Expected to be achieved*; 2024-08-16: *Expected to be achieved*; 2024-08-23: *Expected to be achieved*; 2024-09-09: *Expected to be achieved*
Financial management | Project agreements signed by the NS and the IFRC no longer than 7 days from the DREF/EA approval |  |  | HoD | HoD | RD |  |  | 2024-08-19: *Expected to be achieved*
| After PA is signed by both parties, HoD/project manager to process the Request for Payment to be sent to Treasury within 10 days of DREF/ EA approval |  |  | Ops Leadership Country | HOD | Finance RO |  |  | 2024-08-23: *Expected to be achieved*
| Bank transfer process by IFRC to the NS within 24h after the request for payment is received/approved |  |  | Finance RO | Finance Gva | HOD |  |  | 2024-08-23: *Expected to be achieved*; 2024-08-30: *Expected to be achieved*
| Confirmation from the NSs of the funds received to be obtained within 3 working days from the value date of the transfer |  |  | HoD | HoD | Finance Country |  |  | 2024-08-30: *Expected to be achieved*
Programme delivery | First round of payment received to the target beneficiaries four weeks after the EA launch for sudden onset (when relevant and when CVA is planned) |  |  | Project Manager Country | HoD | Sector lead(s) |  |  | 2024-09-09: *Expected to be achieved*
| NFIs distributed to targetted population within one month of the EA |  |  | Project Manager Country | HoD | Sector lead(s) / Logistics RO |  |  | 2024-09-09: *Expected to be achieved*; 2024-10-09: *% to be noted here*; 2024-11-09: *% to be noted here*
| % of targeted population receiving assistance |  |  | Ops leadership in country | HoD | Sector lead(s) |  |  | 2024-08-23: *% to be noted here*; 2024-09-09: *% to be noted here*; 2024-10-09: *% to be noted here*; 2024-11-09: *% to be noted here*
| % implementation rate of available budget |  |  | Ops leadership in country | HOD | Sector lead(s) |  |  | 2024-08-23: *% to be noted here*; 2024-08-30: *% to be noted here*; 2024-09-09: *% to be noted here*; 2024-10-09: *% to be noted here*; 2024-11-09: *% to be noted here*
Security | Operation is MSR (v.2021) compliant |  |  | HOD | RD | Security team (Country/ Region/ Geneva) |  |  | 2024-08-16: *Expected to be achieved*
| If the country is not MSR, enough resource (HR/Funds) have been allocated to operate in a Red/orange security phase areas |  |  | HOD | RD | Security team (Country/ Region/ Geneva) |  |  | 2024-08-16: *Expected to be achieved*
To report under (color) | To report as
Done or not done (timeliness indicators)
To fill data - % or # or other (as applicable)
1° Note to the person "responsible" , please write in the appropriate column if the task is achieved or not. It is expected that the task is achieved at the "blue" case but feel free to include it in the right column when done.
For the yellow case, please write the % or # in the yellow cases.
2° Please note that these indicators are standardized, consequently they may not apply in specific context. If that the case, feel free to mention "NA" in the Column "E"

## Timeline formula data (hidden)
1 | Achieved
2 | Not achieved
3
4
7
10
14
21
1
2
3